## Sheet1
HPQC Defect ID | Defect Status | Summary | Detection Date | Target Deploy Date | AML/ASP Categorisation
1333 | Under Analysis | DM REC financial mismatches in Amendment supporting file | 2019-03-27 | 18/10/2019 | ASP/AML Financial Mismatch
1429 | Ready For Assurance | RGMA activity has performed both class 3 normal rec and Check to Check reconciliation. This should have ideally triggered only Check to Check rec since DRE or AMR are registered. | 2019-07-24 | 08/11/2019 | ASP/AML Non-Financial Mismatch
1449 | UAT Execution | RGMA activity received in a class 4 period post class change from class 2 to class 4 calculates incorrect volume. | 2019-09-03 | 06/12/2019 | ASP/AML Financial Mismatch
1453 | Fix In Progress | SAP - ASP RCA May-19 | 2019-09-11 | 29/11/2019 | ASP/AML Financial Mismatch
1458 | Ready for Internal Testing | Issue with class 3 read upload process - Non-opening read is inserted between two reads through UBR process and next read has a TTZ of 1, volume is calculated incorrectly through UBR process | 2019-09-13 | 06/12/2019 | ASP/AML Financial Mismatch
1462 | DRS completed | Differences between the total of the K90 lines in the ASP File and the K92 lines in the AML | 2019-09-17 | 22/11/2019 | ASP/AML Financial Mismatch
1463 | Phased Assurance | Incorrect volume calculation for class 3 sites between class change date and first cyclic read received post class change to class 3 | 2019-09-19 | 22/11/2019 | ASP/AML Financial Mismatch
1477 | DRS Needed | Incorrect variance Energy created after NDM prime reconciliation and net off volume and energy getting populated with 0 | 2019-10-11 | 03/01/2020 | ASP/AML Non-Financial Mismatch