## Sheet1
Defect Number | Defect Description | Impact to Amendment Invoice | Simultaneous Deployment dependency | Prerequisite Dependency | AQ Related | Defect Assessment | Assess Links / Dependencies | DRS Status | Defect Fix Status | Testing | Assurance | Retest | Final Assurance | Awaiting CAB | Target Deployment Date | On Target | Defect Status
720 | Prime & Sub Presentation Issue in ASP File | Presentation issue | 761 (also linked to 958 & 1000) |  | No | Completed | Completed | In progress | [6 empty] | 2018-11-08 | Green | In Progress
743 | Issue with billing where a UMR read is at D-1 of an RGMA update | Charge calculation |  |  | No | Completed | Completed | Completed | In Progress | In progress |  |  |  |  | 2018-10-12 | Green | In Progress
761 | Prime Reconciliation Billing Issue - to co-terminus reads only | Charge calculation | 720 (also linked to 958 & 1000) | 720 | No | Completed | Completed | Completed | Completed | Completed | Passed | N/A | N/A | Yes | 2018-11-08 | Green | In Progress
838 |  | Presentation issue |  |  | No | Completed | Completed | [7 empty] | 2018-11-16 | At Risk | In Progress
859 | BW - Missing records in AML | Presentation issue | 920 | UBID - Phase 2 | No | Completed | Completed | [7 empty] | 2018-11-15 | Green | In Progress
863 | Incorrect volume & energy populated for some replacement reads | Charge calculation | 886 | UBID - Phase 2 | Yes | Completed | Completed | Completed | Completed | Completed | Passed | Completed | Passed | Complete | 2018-09-18 | Green | Deployed
886 | Error with read input screen for FINX read | Charge calculation | 863 | UBID - Phase 2 | No | Completed | Completed | Completed | Completed | Completed | Passed | N/A | N/A | Complete | 2018-09-18 | Green | Deployed
906 | Isolation and Reconnection billing trigger not available for capped and clamped sites | Charge calculation |  |  | No | Completed | Completed | Completed | Completed | Completed | Ready |  |  |  | 2018-10-19 | Green | In Progress
920 | AML File - issue with data extraction | Presentation issue | 859 | UBID - Phase 2 | No | Completed | Completed | [7 empty] | 2018-11-15 | Green | In Progress
947 | Variance volume issues in Reconciliation | Charge calculation |  | 859 | Yes | Completed | Completed | Completed | Completed | in progress |  |  |  |  | 2018-11-15 | Green | In Progress
958 | Issue with uploading reads for device removal or exchange Class 4 Prime Sites | Charge calculation |  | 720, 761 & 1000 (886) | No | Completed | Completed | Completed | [6 empty] | 2018-11-08 | At Risk | In Progress
982 | -Implementation of CR307 | Charge calculation |  |  | No | Completed | Completed | Completed | Completed | Passed | Complete | N/A | N/A | Complete | 2018-09-28 | Green | Deployed
1000 | Class 4 prime rec checking co-terminus reads on sub site which was isolated/no devices allocated | Charge calculation | also linked to 958 | 720 & 761 | No | Completed | Completed | Completed | [6 empty] | 2018-11-08 | At Risk | In Progress
1015 | Deemed variance energy incorrectly populated in ASP file | Presentation issue |  |  | No | Completed | Completed | [7 empty] | 2018-11-15 | Green | In Progress
1016 | Incorrect Deemed energy values being populated in ASP files. | Presentation issue |  | 1086 | No | Completed | Completed | Completed | In Progress | [5 empty] | 2018-10-23 | Green | In Progress
1045 | UMR processing is not picking the next actual correctly for the cases where there is an estimated transfer date available for a date greater than UMR read date | Charge calculation |  |  | Yes | Completed | Completed | Completed | Completed | Completed | Failed | Completed | Passed | Complete | 2018-09-18 | Green | Deployed
1048 | ASP mismatch January 2018 amendments invoice | Presentation issue |  |  | No | Completed | Completed | Requested | [6 empty] | 2018-10-04 | Green | In Progress
1049 | Bill doc automatic calculation | Charge calculation |  |  | No | Completed | Completed | Completed | Completed | Passed | Passed | N/A | N/A | Complete | 2018-09-20 | Green | Deployed
1052 | System has generated an incorrect positive/ Negative volume when there is estimated read in rec calculation. TTZ being considered as -1 | Charge calculation |  |  | Yes | Completed | Completed | [7 empty] | 2018-11-13 | At Risk | In Progress
1054 | - LM Scenario - Bill order not created | Charge calculation |  |  | No | Completed | Completed | In progress | [6 empty] | 2018-10-21 | Green | In Progress
1065 | phase 2 data for CR307 | Charge calculation |  | 982 | No | Completed | Completed | Completed | Completed | in progress |  |  |  |  | 2018-10-08 | Green | In Progress
1075 | A Problem record is raised to fix the issue where the MUS/GSR program is giving BC trigger date as "MoveIn" instead of "MoveIn - 2". | Charge calculation |  |  | No | Completed | Completed | Completed | Completed | Completed | Passed | N/A | N/A |  | Deploy with Release 3 | Green | In Progress
1085 | wrong charge calculation in the ASP file presentation | Presentation issue |  |  | No | Completed | Completed | Completed | In Progress | in progress |  |  |  |  | 2018-10-13 | Green | In Progress
1086 | It was found that Duplicate consumption adjustments which are not aligned to the read dates have the net-off issue. The current code perform the netoff against the original complete month period even if there is a split in the billing document variances due to consumption adjustment. This is causing mismatches for those variances where there is a split in the ASP report. This need changes similar to the break-in REC. | Charge calculation |  | UBID - Phase 2 | No | Completed | Completed | Completed | Completed | [5 empty] | 2018-10-23 | Green | In Progress
1108 | Consumption adjustment has not been loaded for ME/CO Site | Charge calculation |  |  | No | Completed | Completed | Completed | Completed | Completed | Failed | Completed | Passed | Complete | 2018-09-20 | Green | Deployed
1109 | Problem with REC INTERFACE Deemed Volume and Energy and Net off incorrect in ASP File. Due to the incorrect values in ZDT_REC_DETAILS table, the net-off values calculated in the ASP file were wrong and hence the mismatch. | Presentation issue |  |  | No | Completed | Completed | [7 empty] | 2018-11-08 | Green | In Progress
1116 | Stranded 8 series documents as they do not match the exact dates of the 3 series | Charge calculation |  | 1114 | No | Completed | Completed |  | Completed | [5 empty] | 2018-10-13 | Green | In Progress
1123 | In SFN process : Class change estimated read should not be considered for tolerance validation and it should get the check read from previous class, in case of last class as (2/3/4) | TBC |  |  | No | Completed | Completed | Completed | [6 empty] | 2018-11-08 | Green | In Progress
1124 | Trying to apply one day CA from 04/03/17 to 04/03/17.Its creating entry in table but bill order is not created, if apply CA with same volume again then also it process without check and creating duplicate entries in CDA table (device scenario:same day corrector installed and meter removed) | Charge calculation |  |  | No | Completed | Completed | Completed | [6 empty] | 2018-11-08 | Green | In Progress
1125 | Received a mail from the user stating that "A Site visit Read has been received on 23.04.2018 959722 which has recalculated the volume/energy back to the last site visit read 15.05.2017 read 664060, giving corrected volume 295662 and energy 3191410". | Charge calculation |  |  | Yes | Completed | Completed | Completed | Completed | [5 empty] | 2018-11-08 | Green | In Progress
859
720 / 761