## Open AQ Issues
Defect / CR No. | Status | Date Defect Raised | Issue Description | Customer Impact | Defect Profiled | Communication Reference No. | Total of affected MPRNs (industry) | Expected Date for Enduring Fix | Date for revised AQ Effective Date | RAG for meeting fix dates | Status Explanation | Linked Ticket Reference Numbers
XRN4740 | Closed |  | For Class 4 sites with AMR fitted the AQ value calculated is incorrect, as both cyclic and sites visit reads are classed as valid reads. XRN4740 has changed the AQ calculation logic to identify energy between each cyclic read as well as the energy calculated between the Check to Check. Where any cyclical reads energy is identified, between two Check to Check reads, then only the energy for the Check to Check will be used for the AQ calculation | Medium | Yes |  | 2745 | Deployed on 16/02/2019 | 2019-11-01 | Complete |  | 979017, A174, A200, A203, 993736
61452 | Open | 2020-02-19 | Reconciliation process is being excluded for prime and sub sites where there has been a class change or a meter exchange or the generation of an estimated shipper transfer read. | Medium | Yes | N/A | 149 | Deployed 04/09/20 | 01/11/2021 | On target | AQs recalculated in October (effective 01/11/21) and awaiting financial adjustment
N/A | Open | N/A | For Class 3 Meter Points, where a meter read is dated between the 5th and the 10th and is accepted within the read submission period, energy has not been calculated for those days, due to the energy factors not being received from Gemini. As the energy is not being calculated for this period of time, this is resulting in the Rolling AQ calculation not using the energy for these days and therefore being understated. | Medium | No | XCE1884 | TBC | N/A | N/A | On target | Resolution options discussed at DSG on 23/03/20 This has been included as a process/design improvement as part of the AQ Taskforce
62164 | Open | 2020-04-14 | Nett-off volume volume/ energy is being incorrectly calculated as zero for class 4 prime sites | Low | Yes | N/A | 159 | Deployed 25/09/2020 | 01/11/2021 | On target | AQs recalculated in October (effective 01/11/21) and awaiting financial adjustment
62381 | Open | 2020-05-13 | When providing a convertor update with a volume correction factor update, without a meter report read (via ONUPD file), a system exception is being incorrectly raised (RU07) | High | Yes | N/A | 5 | TBC | TBC | No resolution dates | Testing of fix is underway
63393 | Open | 2020-08-26 | For an NDM Prime Site, the Sub site volume and energy is not getting calculated if there is an MRU frequency change for the same class | Medium | Yes | N/A | 113 | Deployed 08/01/2021 | 01/11/2021 | On target | AQs recalculated in October (effective 01/11/21) and awaiting financial adjustment
63682 | Open | 2020-09-25 | If a Shipper loads a class change, shipper transfer, Site Fault Notification Read (SFN), Unbundled Meter or CYCL read, followed by an RGMA exchange or removal on D+1, the volume and energy are being incorrectly calculated | Medium | Yes | N/A | 93 | TBC | TBC | No resolution dates | Testing of fix is underway
63691 | Open | 2020-08-28 | A read is not getting loaded in the Prime/Sub table after processing the read through the MOD 700 UBR process for Class 3 prime/sub sites under the EUC band | Medium | Yes | N/A | 15 | Deployed 30/03/2021 | 01/11/2021 | On target | AQs recalculated in October (effective 01/11/21) and awaiting financial adjustment
64026 | Open | 2020-11-20 | The Class change on the Twin Stream Site is creating an FICC record for only one stream in the Staging table, the SFN, DLC and UDR Table | Low | Yes | N/A | 8 | Deployed 23/07/2021 | Expected 01/04/2022 | On target | AQ's to be recalculated and effective as of 1st April 2022
64169 | Open | 2020-12-11 | For a Class 4 Prime site, after performing an NDM Class 4 Prime Reconciliation, the recalculated REC net off Volume and Energy is not getting updated in UK Link | Medium | Yes | N/A | 48 | Deployed 15/03/2021 | 01/11/2021 | On target | AQs recalculated in October (effective 01/11/21) and awaiting financial adjustment
65001 | Open | 2021-03-30 | When a Site Fault Notification Read (SFN) is uploaded in the system for a Class 4 Prime site, the net-off read, volume, and energy are not being retained correctly in UK Link | Medium | Yes | N/A | 1 | Deployed 30/08/2021 | 2021-11-01 | On target | Fix deployed and data correction completed in August. Awaiting financial adjustment
65220 | Open | 2021-05-09 | Reconciliation is not calculating correctly for class 3 prime site as it is using same volume which is present in the system for updating net-off volume and energy. | High | Yes | N/A | 34 | Deployed 03/12/2021 | TBC | On target | Fix deployed. Awaiting business assurance on data correction and then requires financial adjustment
65665 | Open | 2021-07-20 | Final read date for Final Exchange Read and Final Class Change Read is being incorrectly updated in the system when the RGMA effective date is the same as the Shipper transfer effective date | Low | Yes | N/A | 1042 | Deployed 09/10/2021 | 2022-03-01 | On target | Fix deployed and AQ's effective as of 1st March 2022, financial adjustments required
65810 | Open | 2021-08-09 | Volume is being incorrectly updated in the system, when a must read is inserted prior to a Shipper transfer estimated read | Medium | Yes | N/A | 2 | TBC | TBC | No resolution dates | Testing of fix is underway
65922 | Open | 2021-08-23 | An incorrect read is being selected as the next actual read for Class 4 sites with a corrector, where the next read does not have a uncorrected read populated | Medium | Yes | N/A | 4 | Deployed 03/12/2021 | 2022-03-01 | On target | Fix deployed, awaiting financial adjustment
66314 | Open | 2021-10-05 | AQ Correction Requests (.AQI) are being processed and updated within UK Link even though a cancellation request has been received | Medium | No | N/A | TBC | TBC | TBC | No resolution dates | Testing of fix is underway
66366 | Open | 2021-10-12 | Previous read date is being incorrectly used as the Final Exchange Read (FINX) and and Final Class Change Read (FINC) when the appointment date is the same as Shipper move-in date | Medium | Yes | N/A | 43 | Deployed 24/01/2022 | TBC | On target | Fix deployed and awaiting business assurance on data correction
66428 | Open | 2021-10-25 | For a site where a class change occurs from class 4 to 3 on D date followed by shipper transfer on D+10 where the transfer read is estimated, the site is Reconciled and billed till D+10 date. When a Replacement read is loaded for the transfer date on D+10, the previous volume is being incorrectly populated | High | Yes | N/A | 202 | TBC | TBC | No resolution dates | Testing of fix is underway
66429 | Open | 2021-10-25 | For class 4 sites, when inserting a read on the first of the month, two variances are being generated at the end of the previous month following reconciliation (only one variance should be generated) | Medium | Yes | N/A | 8751 | TBC | TBC | No resolution dates | Testing of fix is underway
66623 | Open | 2021-11-22 | Class 4 Prime-sub sites, When Shipper transfer is performed for sub site on D date followed by loading an actual read through a read submission file (within transfer window(D to D+5)) the transfer read estimation is not getting triggered | Medium | Yes | N/A | 0 | TBC | TBC | No resolution dates | Testing of fix is underway
66624 | Open | 2021-11-22 | When a read is submitted by the outgoing Shipper on D-1 for a Prime site, the read is being incorrectly loaded as an active read | Medium | Yes | N/A | 3 | TBC | TBC | No resolution dates | Testing of fix is underway
67274 | Open | 2022-01-24 | Consumption Adjustments for Class 4 sites are not being applied by CMS for one day whereby the Final Class Change Read (FICC) and Final Exchange Read (FINX) are present on the same date and adjustment start date and end date are same in UK Link Consumption Adjustments for Class 2 sites are not being applied where adjustment end date is the same as Shipper end date | Low | No | N/A | TBC | TBC | TBC | No resolution dates | Analysis of fix is ongoing
67319 | Open | 2022-01-31 | When a Site Visit read is inserted between 2 actual reads for Class 1 & 2 DM sites, the Site Visit read insert is not populating the next read date within UK Link | High | Yes | N/A | 8 | TBC | TBC | No resolution dates | Analysis of fix is ongoing

## Closed AQ Issues
Defect / CR No. | Status | Date Defect Raised | Issue Description | Customer Impact | Defect Profiled | Communication Reference No. | Total of affected MPRNs (industry) | Expected Date for Enduring Fix | Date for revised AQ Effective Date | RAG for meeting fix dates | Status Explanation | Linked Ticket Reference Numbers
54138 (1122) | Closed | 2018-08-10 | Multiple RGMA reads (Final Exchange and Report read) recorded in UKLink for the same day is resulting in incorrect one day reconcilaiton. | Low | Yes | XCE1864 | 626 | Deployed on 17/05/2019 | 2019-12-01 | Complete | Data correction & AQ calculation completed however, checks continue on the corrections.
1146 | Closed | 2018-09-06 | Following a Class change from any Class to a Class 3, where an estimated class change read is calcualted following the receipt of an actual read the volume and energy is not calculated between the estimated Class change read and the next actual read. | High | Yes |  | 121000 | Deployed on 06/12/2018 however further MPRNs identified which relates to 1463 (please refer to 1463 for further info) | 2019-11-01 | Complete | Data corrections & AQs re-calculated & issued to customers in AQ notification files on 25th October. AQs effective 1st November 2019. | 954281, 1052608, A137, A142a, A145, A194, A196, A198, A199, 995347, 997176, A229, A255, A259, A296, 1013592, A386, A387
1207 | Closed | 2018-11-15 | Incorrect consumption and energy calculated following a Class change and Convertor removal/exchange. Calculation of consumption to the Convertor removal read instead of calculating back to the Class change read. | Medium | Yes | XCE1853 | 9 | Deployed on 05/04/2019 | 2019-11-01 | Complete | Data corrections & AQs re-calculated & issued to customers in AQ notification files on 25th October. AQs effective 1st November 2019.
1240 | Closed | 2018-12-17 | When Xoserve user has entered reads for Class 2 meter points on behalf of the customer, the read has not created a consumption or energy | Medium | Yes | XCE1853 | 28 | Deployed on 10/05/2019 | 2019-11-01 | Complete | Data corrections & AQs re-calculated & issued to customers in AQ notification files on 25th October. AQs effective 1st November 2019.
1278 | Closed | 2019-01-23 | For Twinstream meter points the allocated aggregate energy is not correct where a 'better estimate' has been created | Low | No | N/A | N/A | Deployed on 21/06/2019 | N/A | Complete | Defect does not impact AQ
1290 | Closed | 2019-01-30 | On receipt of an RGMA flow to update AMR equipment, the read has incorrectly updated Site Visit information | High | No | N/A | N/A | Deployed on 05/04/2019 | N/A | Complete | Defect does not impact AQ
1321 | Closed | 2019-03-14 | Volume is not calculated correctly when Class 4 read (via UMR) is suppressed by asset update (FICC) read causing 1 day reconciliation | Low | Yes | XCE1853 | 169 | Deployed on 17/05/2019 | 2019-11-01 | Complete | Data corrections & AQs re-calculated & issued to customers in AQ notification files on 25th October. AQs effective 1st November 2019.
59187 (1334) | Closed | 2019-03-27 | Following a Class change, any read inserted in the old class period, the subsequent read date is being populated as class change read. Re-rec should only be carried out once the first reconciliation has processed. | Medium | Yes | XCE1875 | 40516 | Deployed on 23/08/2019 | 2020-03-01 | Complete | on target to resolve for 01/03/2020
1341 | Closed | 2019-04-10 | Following the replacement of class change read from class 4 to class 3 the consumption recorded against the class 4 period is being calcualted incorrectly. | Low | Yes | XCE1853 | 14 | Deployed on 28/05/2019 | 2019-11-01 | Complete | Data corrections & AQs re-calculated & issued to customers in AQ notification files on 25th October. AQs effective 1st November 2019.
1349 | Closed | 2019-04-16 | Consumption and energy incorrectly calculated for Class 3 reads received via UBR. First non-opening read received post class change is unable to identify the last read and calculates zero volume. | Medium | N/A | N/A | N/A | Deployed on 05/07/2019 | N/A | Complete | Defect does not impact AQ
60865 (1372) | Closed | 2019-05-10 | For class 4 Prime sites, reconcillation being triggered for both final (FINX) and opening (OPNX) read | Medium | Yes |  | Linked to defect 720 | Deployed on 02/08/2019 | TBC | Complete | The data will be corrected under defect 720
1377 | Closed | 2019-05-15 | Following submission of a meter reading with a 'Round the Clock count' (TTZ), the consumption and energy calculated is a negative value, should be a positive value. | Medium | Yes | XCE1853 | 594 | Deployed on 12/08/2019 | 2019-11-01 | Complete | Data corrections & AQs re-calculated & issued to customers in AQ notification files on 25th October. AQs effective 1st November 2019.
1394 | Closed | 2019-06-06 | Xoserve User, on behalf of the Shipper, is unable to replace a Class change read or shipper transfer read through read entry screen | Low | Yes | XCE1853 | 78 | Deployed on 13/09/2019 | 2019-12-01 | Complete | AQs effective 1st December. | A256a
1395 | Closed | 2019-06-07 | Accepted NDM Meter Readings are not being processed through to reconciliation and AQ, status 'inactive' in the production system | Medium | No |  |  | Deployed 27/09/2019 | N/A | Complete | Defect does not impact AQ
1411 | Closed | 04/07/2019 | The monthly AQ calculation process had been using the incorrect energy to calculate the AQ following an asset update. Affecting Class 1, 2 and 3 sites. | Medium | Yes |  | 771 | Deployed on 12/08/2019 | 01/09/2019 | Complete | Fix deployed, data corrected & AQs re-calculated effective 1st September 2019
1414 | Closed | 12/07/2019 | Where there is a Class change from Class 1 to Class 2, consumption and energy is calculated incorrectly from the Class change start date | Medium | N/A |  | N/A | Deployed 20/09/2019 | N/A | Complete | Defect does not impact AQ
1415 | Closed | 15/07/2019 | When an Xoserve user manually processes an actual read, the consumption and energy is being incorrectly calculated as zero. | Low | Yes | XCE1853 | 3 | Deployed 18/10/2019 | 2019-12-01 | Complete | AQs effective 1st December.
1423 | Closed | 2019-07-23 | For Class 2 sites, an update to consumption/Volume and Energy entered after D+5 should trigger a reconciliation however, it is incorrectly updating original enery for Commodity charging. | Low | No | N/A | N/A | Deployed 06/12/2019 |  | Closed | Defect does not impact AQ, added to 'Issue Register'
59281 (1429) | Closed | 2019-07-24 | Following an RGMA update for a Class 3, a reconciliation and Check To Check reconciliation has been calculated. Only the Check to Check reconciliation should be triggered. | Medium | Yes | XCE1872 | 626 | Deployed 17/01/2020 | 01/12/2019 Remaining 01/03/2020 | Complete
1447 | Closed | 2019-09-03 | AQ calculated when it shouldn't due to the Backstop date created following an AQ Correction. | Low | N/A | N/A | N/A | Deployed 08/11/2019 | N/A | Closed | Defect does not impact AQ, added to 'Issue Register'
1448 | Closed | 2019-09-03 | The AQ calculation process is not using all available reads to calculate the AQ resulting in AQs not being calculated or wrong consumption/energy used to calculate the AQ. | Low | No | N/A | N/A | Deployed 08/11/2019 |  | Closed | Defect does not impact AQ | 1000206, 1000239
60941 (1449) | Closed | 2019-09-03 | Following a Class change from Class 2 to 4, where a meter update is received during the period of Class 4, the energy calculated is incorrect. | Low | Yes | XCE1853 | 170 | Deployed 24/01/2020 | 2020-03-01 | Complete |  | A362a
1454 | Closed | 2019-09-13 | A read on the backstop date has not been used in the Winter Consumption (WC) period calculation. | Medium | N/A | N/A | N/A | Deployed 06/12/2019 |  | Closed | Defect does not impact AQ, added to 'Issue Register' | 1019007
1455 | Closed | 2019-09-13 | Where there is a Shipper transfer opening read and an RGMA report read present on the same day, the system creates a one day reconciliation and rejects a Shipper Agreed Read (SAR) incorrectly. | Low | N/A | N/A | N/A | Deployed 29/11/2019 | N/A | Complete | Data correction or AQ re-calc not required. No impact to AQ calculation
1457 | Closed | 2019-09-13 | Where the monthly AQ process is triggered after the 11th of the month, any reads received after the 10th are being considered in the AQ calculation, it should only consider reads upto the 10th of the month. | Low | N/A | N/A | N/A | Deployed 19/11/2019 | N/A | Complete | Data correction or AQ re-calc not required. No impact to AQ calculation
60950 (1458) | Closed | 2019-09-13 | For Class 4 meter points, where a non-opening read is inserted between two reads (reads received via the UBR file) and where the next read has a riund the clock (TTZ) count of 1, the volume is calculated incorrectly | Low | Yes |  | 15 | Deployed 08/05/2020 | N/A | Complete | Data correction not required
60955 (1463) | Closed | 2019-09-19 | Following a Class change from any Class to a Class 3, where an estimated class change read is calcualted following the receipt of an actual read the volume and energy is not calculated between the estimated Class change read and the next actual read. | Very High | Yes |  | 621500 | Deployed 06/12/2019 | 01/11/19 for 300,000 01/12/19 for 230,000 01/01/20 for 91,500 01/02/20 for 54,098 (data corrections) | Complete | Fix delayed, due to be deployed on 22/11/19. Data corrections & AQ recalculations carried out for 300k during October, revised AQ effective 1st November. Data corrections & AQ recalculations carried out for 230k during November, revised AQ effective 1st December. 91,500 corrections during December & new AQs will be effective 1st January 2020. 54k data corrections found to be incorrect. These have been corrected effective 01/02/90. FYAX datafix completed 24/01/2020. | 954281, A137, A142a, A145, A194, A196, A198, A199, 995347, 997176, A229, A255, A259, A296, 1013592, A386, A387, 1052608, 1057400
60956 (1464) | Closed | 2019-09-19 | Following receipt of a valid read received on a UBR file on (D-1) of the RGMA activity date for a site with DRE installed, the read is accepted calculating incorrect forward and backward volume. | Medium | No | XCE1872 | 536 | Deployed 06/03/2020 | 2020-04-01 | Complete
60958 (1466) | Closed | 2019-09-20 | When reads for multiple MPRNs are processed at once, class 3 prime net-off process is unable to update the reads processed for the individual MPRNs. | Low | N/A | N/A | N/A | Deployed 04/01/2020 | N/A | Complete
60960 (1468) | Closed | 2019-09-25 | On receipt of a replacement read where Check to Check reconciliation has not been processed, incorrect volume & energy is calculated | Low | Yes | XCE1853 | 19 | Deployed 06/12/2019 | 2020-03-01 | Complete |  | A249
1474 | Closed | 2019-10-07 | For a number of meter points the meter installation read is not considered as the trigger for AQ calculation process. | Low | N/A | N/A | N/A | Deployed 08/11/2019 | N/A | Complete | Data correction or AQ re-calc not required. No impact to AQ calculation
1478 | Closed | 2019-10-11 | A system exception is being incorrectly created when there is a mismatch in the volume calculation. | Low | N/A | N/A | N/A | Deployed 20/12/2019 | N/A | Complete | Data correction or AQ re-calc not required. No impact to AQ calculation
60980 (1488) | Closed | 2019-11-06 | Volume calculated incorrectly where a 1 day consumption adjustment recorded between shipper transfer effective date and device removal read (FINX or FINC) | Low | No | XCE1872 | 208 | Deployed 10/01/2020 | 2020-03-01 | Complete
59344 (1492) | Closed | 2019-11-14 | When a Winter Consumption (WC) correction is in progress, receipt of another WC correction for the same effective date should be rejected, currently it is being accepted. | Low | N/A | N/A | N/A | Deployed 07/02/2020 | N/A | Complete | Delayed deployment. No impact to AQ calculation
60984 (1492) | Closed | 2019-11-14 | Winter consumption correction issues | Low | Yes |  | 1272 | Deployed 07/02/2020 | N/A | Complete
1089 / 945 | Closed | 2018-07-12 | The reconciliation process is considering the 'Round the Clock count' (TTZ) on the final read (FINX) when the FINX read fulfills the transfer read request. This in creating an incorrect volume between OPNT and FINX read. | Medium | Yes | XCE1853 | 595 | Deployed on 11/01/2019 | 2019-11-01 | Complete | Data corrections & AQs re-calculated & issued to customers in AQ notification files on 25th October. AQs effective 1st November 2019.
XRN4740 | Closed |  | For Class 4 sites with AMR fitted the AQ value calculated is incorrect, as both cyclic and sites visit reads are classed as valid reads. XRN4740 has changed the AQ calculation logic to identify energy between each cyclic read as well as the energy calculated between the Check to Check. Where any cyclical reads energy is identified, between two Check to Check reads, then only the energy for the Check to Check will be used for the AQ calculation | Medium | Yes |  | 2745 | Deployed on 16/02/2019 | 2019-11-01 | Complete |  | 979017, A174, A200, A203, 993736
61002 (1510) | Closed | 2019-12-13 | Volume & energy duplicated where a Must Read is received on the same day an actual read is received & accepted. | Low | No |  | TBC | Expected 06/03/2020 | TBC | Closed | This defect has been closed & a new defect raised
61008 (1516) | Closed | 2019-12-24 | For Shared Supply Meter Points (SSMP) the AQ is not being calculated as the system is not using the correct asset details. | Low | No |  | TBC | Deployed 24/04/2020 | N/A | Closed | No impact to AQ calculation
61011 (1519) | Closed | 2020-01-03 | Following an AQ correctiion challenging the Formula year AQ and SOQ values effective for 01.04.2020 the system is incorrectly updating the values. | Medium | No | N/A | N/A | Deployed 06/03/2020 | N/A | Complete | No impact to AQ calculation
61074 | Closed | 2020-01-16 | Final removal read (FINC) for Class 3 sites is not being considered for the AQ process (end date derivation) | Low | No |  | TBC | Deployed 24/04/2020 | N/A | Closed | No impact to AQ calculation
61423 | Closed | 2020-02-18 | AQ correction request reason 4 (changing tolerance) which is received along with U01 read is incorrectly allowing the Shipper to cancel the AQ correction on receipt of a C42 record (request for cancellation) | Waiting analysis | N/A | N/A | N/A | Deployed 22/05/2020 | N/A | Complete | No impact to AQ calculation
61647 | Closed | 2020-03-04 | Energy is not updated correctly following read replacement | Medium | No |  | TBC | TBC | TBC | Closed | Followng further analysis, issue no longer exists in the system
61786 | Closed | 2020-03-13 | FYAQ not determined correctly following an AQ correction request effective 1st April. | N/A | No |  | TBC | Expected 05/06/2020 | TBC | Closed | Following further analysis, confirmation that there is no impact to AQ calculation
61747 | Closed | 2020-03-10 | AQ Corrections are incorrectly rejecting whereby a Shipper has submitted a valid read, however is failing tolerance checks when they should be accepted. | Low | No |  | TBC | Deployed 03/07/2020 | N/A | Closed | No impact to AQ calculation
62028 | Closed | 2020-04-01 | When Shippers load a replacement read for an inactive read, the system is incorrectly accepting the read as an active read when it should reject. | N/A | N/A |  | TBC | Expected 03/07/2020 | N/A | Closed | Following further analysis, confirmation that there is no impact to AQ
62060 | Closed | 2020-04-03 | The cyclical read received with read on class change end date should be made inactive to avoid issues with reconciliation | Medium | Yes |  | 77000 | TBC | TBC | Closed | Non AQ Impacting, will be monitored under non AQ impacting defects
62784 | Closed | 2020-06-19 | Where a read is inserted between OPNN and OPNT after reconciliation has been undertaken, the OPNT read is not being considered during the re-rec | High | No |  | TBC | Deployed 06/11/2020 | N/A | Closed | No MPRNs affected in production and therefore no data corrections required
60230 (720) | Closed | 2018-05-15 | Volume and energy calculated incorrectly for Prime and Sub MPRNs. | Medium | Yes | XCE1853 | 32 | Deployed on 30/01/2019 | 2020-10-01 | Closed | Only 2 MPRNs required data correction. Ran through adjustments tool, however no financial adjustments were required. | A158
62513 | Closed | 2020-06-01 | When the Cyclic read is received in the Class 3 period before RGMA activity date (D-1), the incorrect energy values are being recorded | Medium | Yes | XCE1921 | 744 | Deployed 06/11/2020 | 2020-12-01 | Closed | Analysis completed and no financial adjustments required
63139 | Closed | 2020-07-23 | Rec flag for the FINX read was updated as N in the Class 3 Reads File (UBR) Table during the cosmetic exchange without read through ONUPD file | Medium | Yes |  | 732 | Deployed 27/11/2020 | N/A | Closed | No data corrections required as processed via Exceptions monthly - therefore no financial adjustments necessary
63346 | Closed | 2020-08-10 | Volume and Energy is being calculated incorrectly between the Estimated Read (LDEX) and the subsequent Cyclic (CYCL) Read for a Class 3 Meter Point (UBR File) | Low | Yes |  | 1 | Deployed 19/01/2021 | N/A | Closed | No data correction required and therefore no financial adjustment necessary
63486 | Closed | 2020-08-28 | Site visit Reads submitted via Portal are getting accepted, when an SFN Read already exists for a later date, hence breaking the Check to Check Rec period. Therefore should be rejected for Class 1 & 2 Sites | High | Yes |  | 22 | 2020-12-07 | N/A | Closed | No data correction required and therefore no financial adjustment necessary
63494 | Closed | 2020-08-28 | WAALP Values are getting derived based on timezone as UK instead of GMTUK , for which there is a mismatch in Read derivation (NDM Estimation) | High | Yes |  | N/A | Deployed 15/01/2021 | N/A | Closed | Data correction & AQ re-calc not required, therefore no financial adjustment necessary
63566 | Closed | 2020-09-10 | For class 2 sites where there is an AMR (Automatic Meter Reading) fitted, read upload is not happening and creating an exception | Medium | N/A |  | N/A | Deployed 15/01/2021 | N/A | Closed | Exceptions are being managed manually, and therefore data corrections are not required
63851 | Closed | 2020-10-22 | AQ Monthly Notification process is missing T04 & S91 Records in the NRL Files (Notification of Revisions to Live Sites) | High | Yes |  | c. 52,000 | Deployed 11/12/2020 | N/A | Closed | No data correction required
60230 (720) | Closed | 2018-05-15 | Volume and energy calculated incorrectly for Prime and Sub MPRNs. | Medium | Yes | XCE1853 | 32 | Deployed on 30/01/2019 | 2020-10-01 | Closed | Only 2 MPRNs required data correction. Financial adjustments were invoiced in February 2021 | A158
60969 (1477) | Closed | 2019-10-11 | There is an Issue with NDM Prime reconciliation where Rec variance is not correct and positive variance energy updated though the variance volume is negative and net off volume and energy is populated with 0. | Low | Yes | XCE1853 | 188 | Deployed 28/02/2020 | 2020-05-01 | Closed | Financial adjustments were invoiced in February 2021 | A339
60978 (1486) | Closed | 2019-10-23 | Incorrect volume calculated where estimated shipper transfer read has a TTZ1 and asset update read has TTZ 0. | Medium | Yes | XCE1853 | 401 | Deployed 28/02/2020 | N/A | Closed | Defect closed - data correction to be picked up as part of TTZ change XRN5072
60987 (1495) | Closed | 2019-11-15 | Class 3 - Incorrect volume calculation when class change read is estimated with TTZ1 | Low | Yes | XCE1872 | 130 | TBC all TTZ defects to be analyised together | N/A | Closed | Defect closed - data correction to be picked up as part of TTZ change XRN5072
60993 (1501) | Closed | 2019-11-29 | Incorrect volume calculated where Shipper transfer read with a TTZ 1 followed by a Class change with TTZ 0, then received a read with a TTZ 1 for a date after the transfer read but before the Class change read. | Low | Yes | XCE1872 | 50 | TBC all TTZ defects to be analyised together | N/A | Closed | Defect closed - data correction to be picked up as part of TTZ change XRN5072
60994 (1502) | Closed | 2019-11-29 | For Class 3 & 4, following acceptance of a Site Visit read (via SFN) the energy is incorrectly populated when there is a meter and corrector installed | Low | Yes | XCE1872 | 126 | Deployed 08/05/2020 | 2020-07-01 | Closed | Financial adjustments were invoiced in February 2021
61019 (1520) | Closed | 2020-01-07 | When receiving a Site Visit read and an RGMA read on the same day the system has incorrectly processed the reads in the wrong order causing energy and volume to be incorrectly calculated. | Low | Yes |  | 30 | Deployed 07/08/20 | 2020-09-01 | Closed | Financial adjustments were invoiced in February 2021
61024 (1525) | Closed | 2020-01-10 | AQ process is incorrectly using a Point of Sale (POS) read as an active shipper transfer read to calculate the AQ following the receipt of a subsenquent read. | Low | Yes |  | 59 | Deployed 29/05/2020 | 2020-07-01 | Closed | Financial adjustments were invoiced in February 2021
61450 | Closed | 2020-01-24 | Reads with type CM, RD and XO on same date as FINC/FINX reads, to be inactivated | Low | Yes | XCE1894 | 64 | Deployed 15/05/2020 | 2020-07-01 | Closed | Financial adjustments were invoiced in February 2021
61716 | Closed | 2020-03-06 | Incorrect Volume-Energy updated against opening reads (OPNT/OPNX/OPNC) | High | Yes | XCE1894 | 34486 | Deployed 22/05/2020 | 2020-07-01 | Closed | Financial adjustments were invoiced in February 2021
61866 | Closed | 2020-03-18 | While deriving the FYAQ/SOQ values for 01/04/2020 during class change effective on 01st, 2nd and 3rd of Jan 2020, instead of considering the rolling AQ/ SOQ of 01/12/2019 values, the previous year values (01/12/2018) have been considered instead which is incorrect. | High | Yes |  | 228 | Deployed 10/06/2020 | N/A | Closed | No financial adjustments required
62134 | Closed | 2020-04-08 | Where a read is replaced on a class 4 site, the system has created 0 volume between OPNT and FINC reads | Medium | Yes |  | 718 | Deployed 15/08/2020 | 2020-09-01 | Closed | Financial adjustments were invoiced in February 2021
62687 | Closed | 2020-07-03 | The read inserted or replaced for class 3, after a class change from 3 to another, is considering class 3 FICC date as the next read date | High | Yes |  | 8557 | Deployed 28/08/2020 | 2020-11-01 | Closed | No financial adjustments required
62944 | Closed | 2020-07-13 | The RGMA reads that are accepted between site visit reads is breaking Check to Check rec. | High | Yes | XCE1921 | 3 | Deployed 10/11/2020 | 2020-12-01 | Closed | Financial adjustments were invoiced in February 2021
63066 | Closed | 2020-07-15 | For Class 3 meter reads submitted via the UBR file, the system is not recording the last read following update of a meter report and converter installation scenario | Medium | Yes |  | 2 | Deployed 25/09/2020 | 2020-11-01 | Closed | Financial adjustments were invoiced in February 2021
63392 | Closed | 2020-08-26 | Estimated Reads are getting derived incorrectly for the Shipper Transfer; hence shipper transfers incorrectly estimated | High | Yes |  | 53 | Deployed 15/01/2021 | 2021-04-01 | Closed | Financial adjustments were invoiced in May 2021
63394 | Closed | 2020-08-26 | The Class 3 read Tolerance Validation is passing due to an Incorrect CV calculation, when the last actual read date is before the Go-live Date | High | Yes |  | 7000 | Deployed 30/10/2020 | N/A | Closed | No AQ re-calculation required. Resolved defect with customer
63480 | Closed | 2020-08-28 | The Last Check Read Date is getting fetched incorrectly for Twin Stream Sites when Reads are uploaded through Portal, resulting in either the Read wrongly rejected, or a break in the check to check period. | Low | Yes |  | 2 | 2020-12-07 | 2021-02-01 | Closed | Financial adjustments were invoiced in May 2021
63485 | Closed | 2020-08-28 | Class 2 Reads (UDR) File process is unable to perform corrective estimation for Class 2 sites post class change from class 2 to any other class, when the actual read is in the Class 2 period | Medium | Yes |  | 40 | 2020-12-07 | 2021-01-01 | Closed | Financial adjustments were invoiced in February 2021
63487 | Closed | 2020-08-28 | Missing volume and energy for a class 4 meter and converter site | Medium | Yes |  | 32 | Deployed 10/11/2020 | 2020-12-01 | Closed | Financial adjustments were invoiced in February 2021
63726 | Closed | 2020-10-05 | Issue with the Class 3 Prime Process; where the subsequent Actual Read has not considered the Shipper Transfer as the last Read Date | Medium | Yes |  | 0 | Deployed 23/04/2021 | N/A | Closed | No data correction or financial adjustments required
64025 | Closed | 2020-11-20 | In the case of a Class change from 4 to 3, when a replacement read is accepted on the Class 3 start date, the Volume and Energy is not calculated correctly | Medium | No |  | 52 | Deployed 15/01/2021 | 2021-04-01 | Closed | Financial adjustments were invoiced in May 2021
60917 (1424) | Closed | 23/07/2019 | Following an update to a meter (non-physical) the volume which is calculated is based on the opening exchange read (OPNX) as opposed to calculating from the final exchange read (FINX) | Medium | Yes | XCE1875 | 976 | Deployed 26/10/2019 | Ongoing | Closed | Processed through financial adjustments tool. Invoices issued on 30th June 2021
63861 | Closed | 2020-11-20 | When a shipper transfer and an RGMA Activity happen on the same date, and the RGMA Read has fulfilled the shipper transfer Read, the energy is getting updated incorrectly whilst performing the REC | High | Yes |  | 3047 | Deployed 15/01/2021 | 2021-04-01 | Closed | Processed through financial adjustments tool. Invoices issued on 30th June 2021
64157 | Closed | 2020-12-11 | The Volume and Energy for meter and corrector are not being loaded when a device exchange happens after D+5 date of the shipper transfer, where the shipper transfer reads are yet to be estimated (i.e., corrector exchange with reporting meter) created | Medium | Yes |  | 0 | Deployed 23/07/2021 | N/A | Closed | No data correction required
64354 | Closed | 2021-01-22 | AMR removal read is not being loaded correctly in the system. It is impacting check to check reconciliation and the AQ | Medium | No |  | 93 | Deployed 07/05/2021 | N/A | Closed | Data correction not required
64715 | Closed | 2021-02-18 | Where an RGMA update is received between D+6 to D+10 of a Shipper transfer for class 3 sites with a meter-corrector, the system is incorrectly using the estimated uncorrected read to calculate the final read for corrector volume calculation | Low | Yes |  | 0 | Deployed 23/07/2021 | N/A | Closed | No MPRNs impacted, and therefore no data correction required
64839 | Closed | 2021-03-08 | Two actuals read for the same date are getting accepted for class 4 Meter where a convertor is fitted, 1 read should be rejected with rejection code MRE01016. | Medium | Yes |  | 156 | Deployed 07/05/2021 | N/A | Closed | Related to change: CHG0031870 Data correction was not required
64730 | Closed | 2021-02-19 | Incorrect Volume and energy is being calculated where there is 2 consecutive Shipper transfer read replacements. | Medium | Yes |  | 367 | Deployed 25/06/2021 | 2021-08-01 | Closed
65805 | Closed | 2021-08-08 | Transfer read replacement through UMR process is incorrectly failing for tolerance validation post meter exchange exchange on D+1 of transfer date | Medium | Yes |  | 0 | 2021-09-27 | N/A | Closed | Data correction not required as no MPRNs affected
62178 | Closed | 2020-04-15 | Where volume and energy is being incorrectly loaded, the system is not creating an exception | Low | Yes |  | 0 | Deployed 02/10/2020 | 01/11/2021 | Closed | AQ's recalculated in October (effective 01/11/21), however data correction was not required nor financial adjustments
64267 | Closed | 2021-01-05 | Issue with Twin stream site : Volume profiles getting updated incorrectly in the case where a corrector serial number is the same for multiple corrector devices | Medium | Yes | N/A | 1 | Deployed 09/07/2021 | 01/11/2021 | Closed | AQs recalculated in October (effective 01/11/21) and financial adjustments will be invoiced in January 2022
65923 | Closed | 2021-08-23 | On insertion of a site visit read, in a zero consumption period (for class 4 sites), an exception is being incorrectly created | Medium | Yes | N/A | 0 | Deployed 19/11/2021 | N/A | Closed | Deployed19/11/2021 - no data correction required
64367 | Closed | 2021-01-18 | If an RGMA report read is received for a Class 3 site, the read date is populating incorrectly in internal read table. The read type is also updated incorrectly using ‘F’ instead of ‘A’ for actual read or ‘E’ for estimate. This issue then causes an MR07 exception in the system. | High | Yes | N/A | 12500 | Deployed 23/07/2021 | 01/09/2021 | Closed | Financial adjustments completed and invoices sent to customers on w/c 17th January 2022
65375 | Closed | 2021-06-08 | Monthly AQ Roll process incorrectly triggering AQ calculation as part of Class 3 Replacement Reads | Medium | Yes | N/A | 14000 | Deployed 30/07/2021 | N/A | Closed | Financial adjustments completed and invoices sent to customers on w/c 17th January 2022
66028 | Open | 2021-09-03 | For Class 4 sites, when the current Site Notification Read (.SFN) is higher than the previous check read, a positive TTZ count is not being considered and is being defaulted to a TTZ of '0' | Medium | Yes | N/A | 0 | Deployed 24/01/2022 | N/A | Closed | Fix deployed however no data correction required

## Customer Impacts
Impact of Incorrect AQs for Class 1 and Class 2 MPRNs
1. For Class 1 and 2 MPRNs the AQ is used to determine the unit rate applied to transportation charges. If there is a change in the AQ affecting the AQ band this will impact the rate applied to transportation charges.
2. The AQ process will continue to use the erroneous consumption/energy for the AQ calculation until the data has been corrected (or the consumption is no longer within the consumption period for AQ process (upto 36 months)).
3. The AQs provided to the Networks via monthly reporting will be incorrect.
4. Any reports or files sent to customers, for example transfer of ownership files, portfolio reporting, will show the incorrect AQ.
5. AQ displayed on Data Enquiry System (DES) will be incorrect
6. No impact to the SOQ as this is determined by the Shipper
Impact of Incorrect AQs for Class 3 and Class 4 MPRNs
1. Energy Allocation will be inaccurate as the Demand Esimation process uses the AQ to estimate daily energy, this will be corrected via the Reconciliation process once a Meter Reading is received.
2. If the incorrect/energy has casused the MPRN to be in the wrong AQ Band which determines the rate applird therefore will have an impact on transportation changes.
3. The AQ process will continue to use the erroneous consumption/energy for the AQ calculation until the data has been corrected (or the consumption is no longer within the consumption period for AQ process (upto 36 months)).
4. Where the incorrect AQ is used to determine the Formula Year AQ (FYAQ) snapshot taken on 1st December, the FYAQ effective on 1st April will be incorrect. A data fix will be required prior to the end of March to ensure the FYAQ is corrected.
5. Where the AQ is incorrect during the Winter Consumption calculation this may result in incorrect Winter Annual Ration (WAR) band allocation.
6. The AQs provided to the Networks via monthly reporting will be incorrect.
7. Any reports or files sent to customers, for example transfer of ownership files, will show the incorrect AQ and SOQ.
8. AQ & SOQ displayed on Data Enquiry System (DES) will be incorrect