## Slide 1: DSC Delivery Sub-Group
Monday 21st August 2023 – 10:30am

## Slide 2: 1b. Previous DSG Meeting Minutes and Action Updates
The DSG Actions Log will be published on the DSG pages of Xoserve.com

## Slide 3: 2. Changes in Capture

## Slide 4: 2a. Change Proposal – For Initial Overview of the Change

## Slide 5: 2a. Change Proposal – For Initial Overview of the Change
2a.i. XRN 5665 Default New Connection AQ values - Annual Review
2a.ii. XRN 5668 Production Data Back up
2a.iii. XRN 5675 Implementation of 0836S - Resolution of Missing Messages following Central Switching Service implementation and integration with REC Change R0067 and Modification 0855 - Settlement Adjustments for Supply Meter Points impacted by the Central Switching System P1 Incident
2a.iv. XRN 5647 Minor Release Drop 11

## Slide 6: XRN 5665 Default New Connection AQ values - Annual Review
Customer Parties | Impacted parties
Shipper | 
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | 
This vote is to approve the change into development | 
Change Description
Xoserve will be required to compile analysis of the Meter Points within each of the Distribution Network Operators LDZ’s to establish any movement in the average AQ for domestic properties. This analysis will include sites where the Meter Point has received sufficient reads to establish a baseline AQ for New Connections within New Build and Redeveloped Properties.
DSC Service Area Associated Funding Split | Service Area 17: Distribution Network wholly funded activities New service line to be created 100% DNO
Proposed Funding split from Proposer | 100% DNO
Change Type | Non-Regulatory
Priority | Medium
Proposer | SGN
Change Proposal | Link to CP

## Slide 7: XRN 5668 Production Data Back up
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | X
IGTs | X
This vote is to approve the change into development | 
Change Description
As part of MHHS the programme is coordinating a series of production data backups on the 19th August. Although the MHHS programme is limited to Electricity at the moment it has been suggested that we as the GRDA take a copy of our portfolio on this day also. Xoserve will be required to take and store a snapshot of production data on the 19th August 2023. This is similar to snapshots taken in January and November 2020. This will be used for future coordinated testing purposes and will be the new industry baseline.
DSC Service Area Associated Funding Split | Service Area 1: Manage Shipper Transfers Funding Split 100% Shipper
Proposed Funding split from Proposer | NA
Change Type | Regulatory
Priority | High
Proposer | RTS - REC Technical Services
Change Proposal | Link to CP

## Slide 8: XRN 5675 Implementation of 0836S - Resolution of Missing Messages following Central Switching Service implementation and integration with REC Change R0067 and Modification 0855 - Settlement Adjustments for Supply Meter Points impacted by the Central Switching System P1 Incident
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | X
This vote is to approve the change into development | 
Change Description
Implementation of Modification 0836S and Modification 0855 Create a Meter Reading for the CSS Registration Effective Date (CSS EFD Meter Reading) in the UK Link system As this Meter Reading is intended to be used for Customer Settlement – Suppliers and Shippers have asked that this Reading is issued to Shippers via email as soon as possible, including additional information to support agreed readings process being executed. Ideally this should be issued as soon as the Opening Meter Readings are loaded in UK Link systems – from circa 17th August 2023 Once the period to allow the outgoing Shipper to replace the CSS EFD Meter Reading Replacement has expired, in accordance with the business rules in 0836S and 0855 assess materiality and issue adjustments. [Subject to confirmation by Modification 0855 workgroup development, a materiality test may be applied. If applicable, where the energy value derived between the energy determined between the Readings on the CSS Registration Effective Date and UK Link Registration Effective Date is less than or equal to 1,200kWh then the adjustment shall not be undertaken.] Adjustments will follow normal adjustment timetable of issue within M+2 of calculation.
DSC Service Area Associated Funding Split | Service Area 1: Manage Shipper Transfers Funding Split 100% Shipper
Proposed Funding split from Proposer | 100% Shipper
Change Type | Regulatory
Priority | Urgent
Proposer | David Addison, Xoserve
Change Proposal | Link to CP

## Slide 9: XRN 5647 Minor Release Drop 11
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | 
For Information | 
Change Description
This Change Proposal has been raised to create a parent XRN for Minor Release Drop 11. There are 3 changes within this release: XRN5547 Updating the Comprehensive Invoice Master List and INV template XRN5316 Rejecting a replacement read with a pre-Line in the Sand (LIS) read date XRN5651 Updates to class 3 and 4 inner tolerance ranges used in meter read validation process
DSC Service Areas Associated | N/A
Proposed Funding split from Proposer | N/A
Change Type | Release Parent
Priority | Medium
Proposer | Xoserve
Change Proposal | Link to CP

## Slide 10: 2b. Change Proposal Initial View Representations

## Slide 11: 2b. Change Proposal Initial View Representations
None for this meeting.

## Slide 12: 2c. Undergoing Solution Options Impact Assessment Review

## Slide 13: 2c. Undergoing Solution Options Impact Assessment Review
None for this meeting.

## Slide 14: 3. Changes in Detailed Design

## Slide 15: 3a. Design Considerations
XRN5547 - Updating the Comprehensive Invoice Master List and INV template
XRN 5556C – CMS Rebuild Version 1.2
XRN 5604 – Shipper Agreed Read (SAR) exceptions process (Modification 0811S)
XRN 5605 - Amendments to the Must Read process (IGT159V)
XRN 5658 – Allocation of LDZ UIG Based on Straight Throughput Method (Mod0831 / Mod0831A)

## Slide 16: XRN5547 - Updating the Comprehensive Invoice Master List and INV template
Detailed Design

## Slide 17: Background
Change XRN5547 was raised to investigate the following customer pain points:
  The content and format of the Comprehensive Invoices Charge Master List document
  Identification of Charge Types applicable for Domestic Reverse Charge (DRC) and associated clause wording
The detailed design was approved at Change Management Committee on 09/08/2023
Following approval of the design the Comprehensive Invoices Charge Master List document can now be updated to reflect the changes to be implemented on 22nd September 2023

## Slide 18: Detailed Design Summary
Approved Design
Within the Comprehensive Invoices Charge Master List presented in the detailed design change pack, the new VAT code and standard clause were not reflected, as the functional changes had not approved at that point. As these have now been approved, the document has been updated to reflect the agreed details that will be in place following implementation of XRN5547. It also incorporates updates made following customer representation on the design change pack that was issued out for consultation and has subsequently been approved.
Updates to the Comprehensive Invoices Charge Master List document
The following updates have been made to the document:
  VAT code updated against Charge Types subject to the Reverse Charge
  Additional definitions added to some columns following customer representation
  Invoice issue descriptions have been updated to define business days clearly
  Capitalisation within the standard clause statements has been standardised
  Clause wording reference Reverse Charge updated
  Updated links will be added to the glossary ahead of document publication

## Slide 19: Detailed Design Summary
Standard Clause Wording
During project build activities it has been found that the drafted standard clause wording was too large for the existing record fields
Although known as Domestic Reverse Charge (DRC), “Reverse Charge” is the term that is required to be included within the clause so the word “Domestic” has been removed from the previously proposed wording
  “CHARGES ON THIS INVOICE MAY BE SUBJECT TO, AND THEREFORE SHOULD BE ACCOUNTED FOR, UNDER THE UK REVERSE CHARGE. THE RECIPIENT OF THIS INVOICE SHOULD ACCOUNT FOR THE VAT OF ANY CHARGE TYPES INCLUDING THE DRC INDICATOR AT THE APPLICABLE RATE, BASED ON THE VAT EXCLUSIVE SELLING PRICE”

## Slide 20: XRN5556C - Contact Management Service (CMS Rebuild) v1.5 Detailed Design Revision
Detailed Design

## Slide 21: XRN5556C - Contact Management Service (CMS Rebuild) v1.5 Detailed Design Revision
New requirements have been put forward since the last version of the Bulk Contact Logging (BCL), Contact Status Change (CSC), and Contact Resolution Response (CRR) files were last reviewed which necessitates some changes to the field length or domain of existing fields.
Some descriptions have also been updated to provide greater clarity.
Bulk Contact Logging (BCL) file format:
Response files:
The following fields have been removed from the Contact Status Change (CSC) and Contact Resolution Response (CRR) file formats as they are not fields existing in the service:
Interim resolution text
Date rejected (CSC only, not originally included on CRR)
The following field has had the Optionality changed from mandatory to optional as the prioritisation feature isn’t currently a feature in the service, though there is a requirement to introduce in the future:
Top 50 flag
The following field has had the Domain and Length changed following requirement to match published UKLink documentation:
Confirmation number – Domain: T, Length: 10

## Slide 22: XRN5604 – Shipper Agreed Read (SAR)Exception Process (Modification 0811S)
Detailed Design

## Slide 23
Background
Change XRN5604 was raised to provide a remedy for SARs that have failed to be progressed (exceptions) within a reasonable period to be managed under a centralised process facilitated by the Central Data Services Provider (CDSP). The key aspects of this new process will be to:
  Enable either the withdrawing or proposing Shipper to submit a new Corrective Opening Meter Read (COMR)
  Enable a COMR to be submitted where it breaches outer tolerance (where the breach has been acknowledged)
High Level Solution Option 1 was chosen at Change Management Committee on 10th May 2023, to provide the following solutions to the above points:
  Use of the Contact Management Service (CMS) to manage the COMR submission process.

## Slide 24
Detailed Design Summary
The XRN5604 Detailed Design Change Pack contains further details of the change, and is summarised here.
CMS
New contact code ‘SAR’ (“Shipper Agreed”) to be used by the proposing or withdrawing Shipper to submit a COMR.
Allow single requests, or a facility for bulk uploads (Bulk Contact Logging).
Validate the COMR on submission and upload into the Supply Point Register utilising a combination of new and existing validations. New validations listed below:

## Slide 25
Detailed Design Summary
CMS (continued)
Provide mechanism for non-submitting Shipper to reject COMR utilising one of two defined rejection reasons.
Where no rejection is received within 20 Supply Point System Business Days (SPSBD), validate COMR again and pass read to UK Link for upload into the Supply Point Register.
Facilitate exception process where COMR fails to be uploaded due to system issue.
Provide PAC reporting data.
UK-Link
Upload COMR into the Supply Point Register in line with the existing SAR process.
Communicate a successful COMR upload to the submitting and non-submitting party via the Unbundled Read Notification (.URN) file.
Make COMR available to be displayed in Gas Enquiry Service (GES) Online Portal in line with an existing SAR.
Ensure the COMR is utilised in downstream processes in line with an existing SAR.
End

## Slide 26: XRN5605 – Amendments to the Must-Read process (IGT159V)
Detailed Design

## Slide 27
Background
Change XRN5605 was raised to address the current IGT Must Read process, ensuring it becomes fit for purpose by introducing new measures - including:
  Ability to set a flag to prevent a meter from entering the IGT Must Read process.
  Ability to pause meters from entering the IGT Must Read process for a defined number of days, due to reasons of Change of Shipper (CoS), Change of Supplier (CoSup), etc.
  New Performance Assurance Committee (PAC) reporting to allow insight into meter preventions/pausing out of the IGT Must Read process.
High Level Solution Option 1b was chosen at the extraordinary Change Management meeting of 16th June, 2023, to provide the following solutions to the above points:
  Use of the Contact Management Service (CMS) to manage flag setting/unsetting.
  Use of UK Link to apply the new business rules (as per IGT159V)
  Use of the Data Discovery Platform (DDP) to provide new PAC reporting, and update existing customer Must Read dashboard views.

## Slide 28
Detailed Design Summary
The XRN5605 Detailed Design Change Pack contains further details of the change, and is summarised here.
CMS
New contact code ‘KMI’ (“Known Meter Issue”) to set/unset flag that controls entry into the IGT Must Read process.
Allow single requests, or a facility for bulk uploads (Bulk Contact Logging).
Flagging sits outside of the IGT Must Read process.
Flagging a meter that is currently in the IGT Must Read process will update the Must Read open contact.
UK Link
For the monthly IGT Must Read Notification report to Shippers and IGTs:
  Exclude meters flagged with a known meter issue.
  Exclude meters where there is:
    a Smart meter associated
    an Automated Meter Reading (AMR) indicator
    an active Data Communications Company (DCC flag)

## Slide 29
Detailed Design Summary
UK Link (continued)
  Pause meters for a defined number of days, where the CDSP detected:
    a Change of Shipper (CoS) event
      including a Supplier of Last Resort (SoLR) event
    a Change of Supplier (CoSup) event
  Validate uploaded meter reading is not older than a set number of days.
DDP
Consequential changes caused by IGT159V on existing views and dashboards.
Provision of new PAC reports, including:
  Changes to existing user access rights, to allow the new PAC reports to be accessed.
Customer self-serve facility to download report/s of meters having a meter issue flag set.

## Slide 30: XRN5658 - Allocation of LDZ UIG to Shippers Based on a Straight Throughput Method (Mod 0831) and Allocation of LDZ UIG to Shippers (Class 2, 3 and 4) Based on a Straight Throughput Method (Mod 0831A)
Detailed Design

## Slide 31: XRN5658 - Allocation of LDZ UIG to Shippers Based on a Straight Throughput Method (Mod 0831) and Allocation of LDZ UIG to Shippers (Class 2, 3 and 4) Based on a Straight Throughput Method (Mod 0831A) Detailed Design Overview
XRN5658 seeks to implement changes that are being proposed by industry that relate to the Unidentified Gas (UIG) Weighting Factors and how these values are applied to Shipper Allocations
The associated CDSP changes included within XRN5658 relate to UNC Modification 0831 / 0831A respectively In summary, Modification 0831 proposes the following key changes;
  UIG weighting factors are proposed to be permanently set to 1 for ALL EUCs and Classes;
  All LDZ System Exit Points will have the allocation factor of 1;
  As a result, UIG will be allocated to all sites based on throughput.
Alternatively, Modification 0831A proposes that UIG weighting factors are permanently set to 1 for all Class 2, 3 and 4 Supply Meter Points (SMPs) only, with UIG weighting factors set to 0 for all Class 1 sites - effectively exempting Class 1 SMPs from UIG allocation
Further details of the proposed changes can be found within the Detailed Design Change Pack on Xoserve.com

## Slide 32: XRN5658 - Allocation of LDZ UIG to Shippers Based on a Straight Throughput Method (Mod 0831) and Allocation of LDZ UIG to Shippers (Class 2, 3 and 4) Based on a Straight Throughput Method (Mod 0831A) Next Steps
UNC Modification 0831 / 0831A are to be considered by UNC Panel on 17th August prior to issuing out for consultation
Following UNC Panel decision on 21st September, both Modifications will be provided to the Authority for a decision
The timescales for an Authority decision on Modifications’ 0831 and 0831A are currently unknown but are anticipated to be made in 2023
Changes will only be made if Authority decision confirms approval of the changes proposed in either of the Modifications
Subject to approval, the go live date must be the 1st day of a given calendar month – with CDSP requiring a notice period of approx. 5-6 weeks before the required Implementation Date
Further communication on implementation activities will be provided to DSC customers and via Change Management Committee following an Authority decision

## Slide 33: 4. Release/Project Updates

## Slide 34: 4. Release/Project Updates
4b. June 23 Major Release
4c. November 23 Major Release

## Slide 35: XRN5562 – June 23 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, implementation was completed successfully on 24/06. The project has now entered the post implementation support (PIS) period, planned to complete on 28/07. Progress update: First usage evidence review and approval for XRN4990 completed First usage evidence approval for XRN5091 on track and due 27/07 Update of all documentation for handover completed Release closedown document update completed PIS exit go/no go meeting arranged for 28/07 Change close down report to be delivered 31/08 Decision in August ChMC: No decision required |  | Implementation completed on 24th June | 
Risks and Issues | Medium 67703 There is a risk that all the 1st usage scenarios might not occur during the PIS period and therefore first usage evidence will be unavailable for such scenarios. Mitigation Action - Agreed with BPCs that UAT evidence will be provided for any scenarios that have not occurred during PIS. |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5091 - Deferral of creation of Class change reads at transfer of ownership XRN4990 - Biomethane Sites with Reduced Propane Injection​ |  |  | 
Complete
On Track
At Risk
Overdue
Slide updated on 25th July 2023

## Slide 36: XRN5629 – November 23 Major Release- Status Update
Slide updated on 25th July 2023
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, BER was approved in ChMC on 10/05. Currently in system testing phase, which commenced on 12/06, implementation on track for 04/11, with contingency implementation available for 11/11 Progress update: UK Link build completed as per plan on 14/07 UK Link system testing execution in progress, on track to complete by 11/08 UK Link user acceptance testing preparation on track to commence on 31/07 System test and user acceptance testing phase timelines extended to complete additional testing and assurance, no impact to overall testing completion and delivery costs Decision in August ChMC: None |  | Implementation date of 4th November, the contingency date is 11th November | 
Risks and Issues | XRN5482:There is a risk that the Shipper Constituency does not prioritise XRN5482 into the current Discovery sprint schedule to align delivery for the November 23 Release, this may increase the cost for delivery of XRN5482 as a standalone Discovery delivery, however, this is within the scope of the BER XRN5186: There is a risk that that following discussions with Networks/Shippers, the industry requests an enhanced solution for XRN5186 go live in order to avoid non-compliance with MOD0701,this may increase the BER cost and extend delivery timelines for XRN5186 |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5186 - MOD0701 – Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs XRN5482 - Replacement of reads associated to a meter asset technical details change or update (RGMA) |  |  | 
Complete
On Track
At Risk
Overdue

## Slide 37: 5. Change Pipeline

## Slide 38: Change Delivery Plan January 23 – March 24
February 23 - Major Release (XRN5533)
XRN4900, XRN4978, XRN4990, XRN4989, XRN4992b, XRN5298
Jan-23
Aug-23
June 23 - Major Release (XRN5562)
XRN5091
Apr-23
Dec-23
Mar-24
November 23 – Major Release (XRN5629)
XRN5186, XRN5482
XRN4713
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative Implementation Date – Changes are scoped for delivery – Funding and/or Implementation Date not yet approved by ChMC
= Delivered on Target Implementation Date
Delivery Key
Slide produced 24th July 2023
March 23 - Adhoc Release (XRN5575)
XRN5379, XRN5143
XRN5595
XRN5555
February 24 – Major Release
XRN5604 | XRN5605 | XRN5607
XRN5535A
XRN5567
Minor Release 12 XRN5454
November 23 – Adhoc Winter Release
XRN5604 | XRN5605
XRN5652
Minor Release 11
XRN5651
XRN5547
XRN5316
*Scope Decision required @ August ChMC
XRN5658

## Slide 39: Change Pipeline - Delivery Plan - January 2023 – June 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Delivered / Firm / Indicative
5555 | Amend existing Large Load Site Reporting | SGN | DN | DN | N/A | 31st January 2023 | Adhoc | Delivered
4900 | Biomethane/Propane Reduction | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Delivered
4978 | Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | British Gas | Shipper | Shipper | £90.6k | 25th February 23 | Major | Delivered
4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 – MOD 0664 | SSE | Shipper | Shipper | £232k | 25th February 23 | Major | Delivered
4989 | Residual AMT activities | CDSP | Shipper | Shipper | N/A | 25th February 23 | Major | Delivered
4992 | XRN4992 - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | Total | Shipper DN | Shipper DNO | £108.7k | 25th February 23 | Major | Delivered
5298 | H100 Fife Project – Hydrogen Network Trial | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Delivered
5595 | Changes to the REC Switching Operator Outage Notification Lead Time (R0055) | Xoserve | Shipper | N/A | N/A | 25th Feb 23 | Major | Delivered
5535A | Processing of CSS Switch Requests Received in ‘Time Period 5’ | Xoserve | All DSC Customers | Shipper | £44k | 10th March 23 | Adhoc | Delivered
5379 | Class 1 Read Service Procurement Exercise - MOD0710 (DM Sampling) | Xoserve | Shipper DN | Shipper | £150k | 1st April 2023 | AdHoc | Delivered
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | Cadent | DN | WWU, Cadent, NGN only | £75k | 1st April 2023 | AdHoc | Delivered
5091 | Deferral of creation of Class change reads at transfer of ownership | EDF | Shipper | Shipper | £200k | 24th June 23 | Major | Delivered
4713 | Actual read following estimated transfer read calculating AQ of 1 | Npower | Shipper | Shipper | £7k | 27th June 2023 | Adhoc | Delivered

## Slide 40: Change Delivery Plan - June 2023 – March 2024
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5606 | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers (Modification 0813) | NGT | NGT Shipper Supplier | NGT | N/A | Rejected by Ofgem on 20th July | N/A | N/A
5652 | Enabling Direct Contractual Arrangements with Consumers for Demand Side Response (Mod0844) | NGT | NGT Shipper DN / IGT | NGT | Tbc | Immediately Following Ofgem Decision (expected August 23) | Adhoc | Indicative
5651 | Updates to Class 3 & 4 Inner Tolerance Ranges used in Meter Read validation process | Centrica | Shipper | Shipper | Tbc | 22nd September 23 | Minor (Drop 11) | Firm
5316 | Rejecting Pre LIS Replacement Reads | Xoserve | Shipper | N/A | N/A | 22nd September 23 | Minor (Drop 11) | Firm
5547 | Updating the Comprehensive Invoice Master List and INV template | Eon | Shipper DN | Shipper | N/A | 22nd September 23 | Minor (Drop 11) | Firm
5482 | Replacement of reads associated to a meter asset technical details change or update (RGMA) | Scottish Power | Shipper | Shipper DN | £300k | 4th November 23 | Major | Firm
5186 | *MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | NGN | Shipper DN | Shipper DN | £200k | 4th November 23 | Major | Firm
5604 | Shipper Agreed Read (SAR) exceptions process (Modification 0811S) | SEFE | Shipper | Shipper | £150k | November 23 / February 24 | Adhoc | Indicative
5605 | Amendments to the must read process (IGT159V) | Centrica | Shipper IGT | Shipper IGT | £190k | November 23 / February 24 | Adhoc | Indicative
5567 | Implementation of Resend Functionality for Messages from CSS to GRDA (REC CP R0067) | Xoserve | All DSC Customers | Shipper | £93k | 6th December 2023 | Adhoc | Indicative
5454 | SoLR Reporting Suite | EDF | Shipper | Shipper | N/A | December 23 | Minor (Drop 12) | Indicative
5658 | Allocation of LDZ UIG Based on Straight Throughput Method (Mod0831 / Mod0831A) | SSE Brook Green | Shipper | Shipper | Tbc | *6 weeks following Ofgem Decision February 24 | Adhoc | Indicative
5607 | Update to the AQ correction processes (Modification 0816S) | EON Next | Shipper DN IGT | Shipper | Tbc | February 24 | Major | Indicative

## Slide 41
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5531 | Hydrogen Village Trial | SGN | All DSC Customers | DN Decarb | £400k | Tbc | Major | N/A
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Tbc | Tbc | Tbc | N/A
5573B | Updates to the Priority Consumer process (as designated by the Secretary of State for Business, Energy, and Industrial Strategy - BEIS) | Xoserve | Shipper DN IGT | Tbc | Tbc | Tbc | Tbc | N/A
5585 | Flow Weighted Average Calorific Value - Phase 2 Service Improvements | Cadent | DN | DN | Tbc | Tbc | Tbc | N/A
5614 | Improving IGT SMP New Connection Process to support accurate and timely Supplier Registrations | BUUK | Shipper IGT | Shipper IGT | Tbc | Tbc | Tbc | N/A
5615 | Establishing/Amending a Gas Vacant Site Process (Modification 0819) | Centrica | Shipper DN IGT | Shipper DN | Tbc | Tbc | Tbc | Tbc
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | Tbc | Tbc | Tbc | N/A
5635 | H100 (UNC Mod799) Consequential Gemini Change | NGT | NGT DN | NGT DN | Tbc | Tbc | Tbc | Tbc
5641 | Addition of Market Sector Code to specific Supply Point Data Reports | NGN | DN | DN | N/A | September 23 | Adhoc | Indicative
5665 | Default New Connection AQ values - Annual Review | SGN | DN Shipper | DN | N/A | N/A | N/A | N/A
Change Backlog Details

## Slide 42: Change Backlog – On Hold Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
4914 | *Mod0651 – Retrospective Data Update Provisions* | Cadent | Shipper DN | Tbc | £1.8m – £2.4m | Tbc | Major | N/A
5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Xoserve | Shipper DN IGT | Tbc | Tbc | Tbc | Tbc | N/A
5187 | MOD0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Gazprom | Shipper DN | Shipper DN | Tbc | Tbc | Tbc | N/A
5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at Transfer | CDSP | Xoserve | Shipper | Tbc | Tbc | Tbc | N/A
5453 | GSOS 2, 3 & 13 Payment Automation | SGN | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Tbc | N/A
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
*Mod0651 : 24.07.23 - Change Status remains on hold and will be reviewed on a monthly basis with ChMC – in line with request from UNCC

## Slide 43: 6. AOB

## Slide 44: Annex – For Information

## Slide 45: 7. DSC Change Management Committee Update
ChMC Meeting 9th August 2023

## Slide 46: Change Management Committee Update –09.08.2023 ChMC Meeting
The Change Management Committee post meeting update can be found here. ​

## Slide 47: 8. REC Change Update

## Slide 48: Introduction
The following 10 slides have been included in this months CoMC pack to give you an overview of the ongoing REC Changes, we have broken these down into the following sections:
In progress – we are currently progressing through the Change journey
Under Prioritisation Review by REC Code Managers – due to CM workload/prioritisation
Expected incoming Impact Assessments
Note: We are currently undertaking a review of all REC Change and have began removing Changes which we have confirmed have no impact to Gas services. In the coming months, we will continue to monitor the Changes listed and add/remove from this pack as required.
Further information on the Changes can be found on the REC Portal

## Slide 49: REC Change Pipeline – In progress
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release | REC Priority | Attachments
R0063 | Addition of key information to all Service Now tickets | N/A | St Clements Ltd (on behalf of DNOs) | - | Consultation | 18/08/23 – Consultation closeout | 12/04/23 | Medium | N/A
This Change was raised to improve the information that’s included on DCC’s Service Now Tickets which have been asynchronously rejected. We interact with DCC via SNow so we need to monitor and input into development. |  |  |  |  |  |  |  |  | 
R0067 | Introduction of CSS refresh functionality | XRN 5567 / UNC Mod 836 | Capgemini (RTS) | GRDS | Approved – Awaiting implementation | Ongoing – Clarification of requirements needed, awaiting stand up of delivery team | 06/12/23 | High | High
This Change will introduce a resend and refresh functionality to help with the message interactions between the CSS and Switching Data Service Providers. Currently, there are cases where messages are being received after Gate Closure or not being received at all. We are one of the impacted Service Providers which means this Change is very important to us so that we are able to complete customer switches successfully. |  |  |  |  |  |  |  |  | 
Please note that we have provided our view of the Change summary and impacts however we recommend that DSC Customers monitor the REC Portal to form their own opinion regarding the impact to their organisation
Currently working on
Key:
Upcoming
Monitoring
Early Engagement

## Slide 50
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release | REC Priority | Attachments
R0071 | DCC access to EES and GES | N/A | DCC | GES | Initial Assessment | 03/08/2023 – DIA expected | TBC | Medium | N/A
As the CSS Provider and Switching Operator, DCC have requested access to GES in order to help resolve Service Now tickets. This Change seeks to introduce a new Enquiry Service User Category to the Data Access Schedule and to reflect the required data item access in the Data Access Matrices. We are currently in early engagement with our Service Provider and the DCC to work through the scenarios that are impacting them to find the best resolution and required data items. |  |  |  |  |  |  |  |  | 
R0080 | Improvements to ‘Failed to Deliver’ CSS Messages | N/A | DCC | - | Service Provider Impact Assessment | TBC – IA currently with DCC | TBC | Medium | N/A
This Change Proposal has been raised to explore how and why, since CSS Go-Live, a number of messages have not been successfully delivered due to failures of CSS User's gateway. This results in CSS exhausting the 12-hour retry period. We are keen that we monitor this Change to ensure that there are no impacts to any current message related Change Requests or the way in which we send and receive messages from CSS. |  |  |  |  |  |  |  |  | 
R0088 | Make Shipper NExA values available on the GES portal | XRN 5186 MOD 0701 | Xoserve | XRN 5186 | Final Assessment | 30/08/2023 – Final Change report issued to TEP | 03/11/23 | Medium | N/A
XRN 5186 - Modification 0701: Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs makes additional information available to GES Users which require reflection in the REC. Although all of the technical change has already been developed. |  |  |  |  |  |  |  |  | 
Currently working on
Key:
Upcoming
Monitoring
Early Engagement

## Slide 51
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release | REC Priority | Attachments
R0092 | DCC Service Level Agreements for the Switching Incentive Regime | N/A | DCC | GES | Solution Development | 10/08/2023 – Bi Weekly Working Group | N/A | Medium | N/A
This Change was raised to review the current Service Level Agreements (SLAs) that are outlined in the REC Service Definition. As the requirements for the Central Switching Service (CSS) were identified during the Design, Build and Test Phase of the Ofgem-led Switching Programme, DCC are proposing that an assessment takes place to ensure that the requirements are appropriate for the physical systems design and the actual behaviours of users, compared to the assumptions that were made in the early design phase. |  |  |  |  |  |  |  |  | 
R0096 | CSS Message Regeneration Functionality | N/A | RTS (Capgemini) | - | Service Provider Impact Assessment | TBC – IA currently with DCC | TBC | Medium | N/A
This Change was raised to identify and regenerate messages from CSS that failed initial generation, such that the message recipient is not impacted. We are keen that we monitor this Change to ensure that there are no impacts to any current message related Change Requests or the way in which we send and receive messages from CSS. |  |  |  |  |  |  |  |  | 
Currently working on
Key:
Upcoming
Monitoring
Early Engagement

## Slide 52
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release | REC Priority | Attachments
R0110 | A review of Supplier access to data on GES | N/A | Scottish Power | GES | Initial Assessment | 03/08/2023 – DIA expected | TBC | Medium | N/A
This Change was raised in order to review the data items that can currently be viewed by Supplier in the Gas Enquiry Service. Scottish Power have come across some issues internally as they don’t currently have access to some items in the Shipper portfolio. We have been assessing the data items that have been requested in the DAM and are working towards the DIA stage of the process. |  |  |  |  |  |  |  |  | 
Currently working on
Key:
Upcoming
Monitoring
Early Engagement

## Slide 53
Title | Description | XRN | Proposer | Impact/ Funding | Status | Next Action date | Release | Priority | Attachments
R0048 | DCC Service Organisation Control 2 (SOC2) Assessments | N/A | DCC | - | Solution development | TBC – Awaiting additional information from DCC | TBC | Low | 
Currently, the CSS Provider is obligated to undertake system organisation control type 2 (SOC2) assessments on the CSS’s cloud-based infrastructure. This Change was raised to assess if the SOC2 assessment provides a proportionate level of assurance or the best value for money and if it should be change to ‘independently assessed’. We are monitoring to determine whether there are impacts to GRDS / GES. |  |  |  |  |  |  |  |  | 
R0070 | Provision of Enduring Test Environments | N/A | Capgemini | GRDS, GES | Solution Development | TBC- Awaiting Impact Assessment from Code Managers | Standalone | High | N/A
This Change was raised to introduce an obligation under the Retail Energy Code for the CSS or the Switching Operator (SO) to provide enduring test environments for REC parties to make the necessary system changes for REC Change Proposals (CPs) or internal system updates. We need to monitor this to ensure that the obligations on GRDS are understood, and that we contribute to the development of this Change. |  |  |  |  |  |  |  |  | 
R0071 | DCC access to EES and GES | N/A | DCC | GES | Initial Assessment | 03/08/2023 – DIA expected | TBC | Medium | N/A
As the CSS Provider and Switching Operator, DCC have requested access to GES in order to help resolve Service Now tickets. This Change seeks to introduce a new Enquiry Service User Category to the Data Access Schedule and to reflect the required data item access in the Data Access Matrices. We are currently in early engagement with our Service Provider and the DCC to work through the scenarios that are impacting them to find the best resolution and required data items. |  |  |  |  |  |  |  |  | 
REC IA Demand
Currently working on
Key:
Upcoming
Monitoring
Early Engagement

## Slide 54
Title | Description | XRN | Proposer | Impact/ Funding | Status | Next Action date | Release | Priority | Attachments
R0110 | A review of Supplier access to data on GES | N/A | Scottish Power | GES | Initial Assessment | 03/08/2023 – DIA expected | TBC | Medium | N/A
This Change was raised in order to review the data items that can currently be viewed by Supplier in the Gas Enquiry Service. Scottish Power have come across some issues internally as they don’t currently have access to some items in the Shipper portfolio. We have been assessing the data items that have been requested in the DAM and are working towards the DIA stage of the process. |  |  |  |  |  |  |  |  | 
REC IA Demand
Currently working on
Key:
Upcoming
Monitoring
Early Engagement

## Slide 55
REC Related XRN Changes
Description | XRN | Proposer | Impact/ Funding | Status | Next Action date | Release Type | Priority
Resolution of Address Interactions between DCC and CDSP | XRN 5546 | Xoserve | GRDS | Under development | 13/09/2023 – Industry meeting. Ongoing investigation and discussion with DNs | TBC | Medium
Currently working on
Key:
Upcoming
Monitoring
Early Engagement

## Slide 56: (Gas) REC Change Pipeline - Under Prioritisation Review
Title | Description | Status
R0049 | Intellectual Property Rights and Services Data Main Body changes | Initial Assessment
R0051 | Switch Request Objections (Change of Occupier) | Initial Assessment
R0056 | EES/GES additional service request for Housing Associations to be added to the Matrix | Initial Assessment
R0068 | REC Data Protection Changes | Initial Assessment
R0069 | Amendments to Sample Access Agreement | Initial Assessment
R0071 | DCC access to EES and GES | Initial Assessment
R0075 | Enabling Software Product Qualification | Initial Assessment
R0081 | CSS Market message retry strategy | Initial Assessment
R0082 | Formalising the Submission of PPMIP Unallocated Transaction Report (UTR) Files | Initial Assessment
R0087 | MAP GES data access | Initial Assessment
R0089 | Removal of Pre-COVID AQ Value from Data Access Matrix | Initial Assessment
R0094 | Clarify obligations on gas meter exchanges that occur close to CoS | Initial Assessment
R0095 | Changes to allow DNOs to reinstate disconnected MPANs | Initial Assessment
R0099 | CSS End User Obligations | Initial Assessment
R0100 | Update to Error Handling Documents | Initial Assessment
R0104 | Clarifying requirement for continuous billing following an Erroneous Switch | Initial Assessment

## Slide 57: (Gas) REC Change Pipeline - Under Prioritisation Review
Title | Description | Status
R0105 | Review of ONAGE SLAs | Initial Assessment
R0106 | Performance Assurance Report Catalogue V5.1 | Initial Assessment
R0107 | CSS Message Time Stamping | Initial Assessment
R0109 | Aligning electricity and gas timescale requirements for sharing Meter Technical Detail information | Initial Assessment
R0110 | A review of Supplier access to data on GES | Initial Assessment
R0111 | Provision of Grid Supply Point Group ID from a Postcode search | Initial Assessment
R0112 | Supplier compensation for Network Party driven MPXN or GSP Group changes | Initial Assessment
R0113 | Data Specification Housekeeping and Clarifications | Initial Assessment
R0115 | Frequency and content of CSS reports on switching via the DCC portal | Initial Assessment
R0116 | TPI access to the Meter Asset Manager data via the GES | Initial Assessment
R0117 | Retrospective Implementation of Distribution Code Use of System Agreement (DCUSA) DCP 383 | Initial Assessment
R0118 | Review of Schedule 12 and processes to manage access to data | Initial Assessment
R0119 | Annulment Definition | Initial Assessment
R0120 | Search GES API using Meter Serial Number | Initial Assessment
R0121 | SDEP Review Improvements (1) - Process Types and escalations | Initial Assessment

## Slide 58: (Gas) REC Change Pipeline - Under Prioritisation Review
Title | Description | Status
R0122 | SDEP Review Improvements (2) - Usability | Initial Assessment
R0123 | SDEP Review Improvements (3) – Look and feel | Initial Assessment
R0124 | SDEP Review Improvements (4) - Reporting | Initial Assessment
R0125 | SDEP Review Improvements (5) – multilateral Erroneous Switches | Initial Assessment
R0126 | SDEP Review Improvements (6) – SDEP User Guide and Obligations | Initial Assessment
R0128 | Removal of CSS Business Rule 1177 to reflect OFAF optionality | Initial Assessment
R0129 | Clarifying Event of Default requirements | Initial Assessment
R0130 | Updates to the Data Access Matrix | Initial Assessment
R0131 | Creation of new Enquiry Service User Category | Initial Assessment
R0132 | Change the Logical Format of the J0001 (DI50001) ‘Market Participant Role Code’ data item to Char(2) | Initial Assessment
R0134 | VLP data access requirements | Initial Assessment
R0135 | Add DESNZ to Schedule 12 | Initial Assessment
R0136 | Change to REC Schedule 22 Market Stabilisation Charge (MSC) | Initial Assessment
R0137 | Introducing Third Party Intermediary (energy broker) assurance and accreditation | Initial Assessment

## Slide 59: 9. Portfolio Delivery

## Slide 60: 9. Portfolio Delivery Overview POAP
The POAP is available here.