## Slide 1: DSC Delivery Sub-Group
Monday 20th January 2025

## Slide 2: 1b. Previous DSG Meeting Minutes and Action Updates
The DSG Actions Log will be published on the DSG pages of Xoserve.com

## Slide 3: 2. Changes in Change Development

## Slide 4: 2a. Change Proposal – For Initial Overview of the Change

## Slide 5: 2a. Change Proposal – For Initial Overview of the Change
2a.i - XRN5866 Change to EIC Code(s) within Gemini
2a.ii - XRN5872 Updates to the Annual Quantity (AQ) amendment process (Modification 0876S)

## Slide 6: XRN5866 Change to EIC Code(s) within Gemini
Customer Parties | Impacted parties
Shipper | Y
Distribution Network Operators (DNOs) | 
National Gas Transmission | Y
IGTs | 
This vote is to approve the change into development | 
Change Description
This Change Proposal has been raised as National Gas require the Energy Identification Code (EIC) in the Gemini system to be updated from the National Grid EIC of 21X-GB-A-A0A0A-7 to the National Gas EIC of 55XNATIONALGASTC. Based on initial analysis, the proposed change will require a data fix in Gemini to amend the EIC Value from the National Grid EIC to National Gas EIC in the respective Gemini database. This will allow the system to consider the appropriate National Gas EIC Code for all file/message validation and exchanges with TSOs, PRISMA and Shippers.
DSC Service Area Associated Funding Split | N/A- Gemini investment funded
Proposed Funding split from Proposer | N/A
Change Type | Non Regulatory
Priority | Medium
Proposer | National Gas
Change Proposal | Link to CP

## Slide 7: XRN5872 Updates to the Annual Quantity (AQ) amendment process (Modification 0876S)
Customer Parties | Impacted parties
Shipper | Y
Distribution Network Operators (DNOs) | Y
National Gas Transmission | 
IGTs | Y
This vote is to approve the change into development | 
Change Description
This change is seeking to update the current Annual Quantity (AQ) amendment process which is available for Shippers to utilise in specific scenarios where the AQ for a Supply Meter Point (SMP) is not believed to be accurate. Based on this, Shippers are detailed as an impacted party. DNOs and IGTs are also considered impacted parties as the outcome of the amendments impact the AQ on SMPs in their network area. This DSC Change Proposal seeks to implement the CDSP related deliverables in line with those proposed under UNC Modification 0876S – which will add clear validation criteria to reason code 2 to ensure that it is used in line with what is outlined within UNC.
DSC Service Area Associated Funding Split | Service Area 2 - Monthly AQ Processes. 100% Shipper
Proposed Funding split from Proposer | Proposer and Modification work group view is that the identified funding split of 100% Shipper is appropriate.
Change Type | Regulatory
Priority | High
Proposer | Sefe
Change Proposal | Link to CP

## Slide 8: 2b. Change Proposal Initial View Representations

## Slide 9: 3a. Design Considerations
2b - None for this meeting

## Slide 10: 2c. Undergoing Solution Options Impact Assessment Review

## Slide 11: 3a. Design Considerations
2c - None for this meeting

## Slide 12: 3. Changes in Detailed Design

## Slide 13: 3a. Design Considerations
3a - None for this meeting

## Slide 14: 3b. Requirements Clarification
3b – None for this meeting

## Slide 15: 4. Release/Project Updates

## Slide 16: 4. Release/Project Updates
4a. XRN5825 Minor Release drop 13
4b. XRN5818 February 25 Major Release Update
4c. June 25 Major Release proposed scope
4d. XRN5778 November 24 Major Release – Implementation Update
4e. DDP Update

## Slide 17: 4a. Minor Release 13 Update

## Slide 18: XRN5825 – Minor Release 13 - Status Update
Slide updated on 02nd January 2025
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking to a Green status. Minor Release 13 was successfully implemented on 6th Dec. First usage activities are complete, and we exited the post-implementation support phase with no issues raised. Closedown activities are ongoing with approval of the CCR at February ChMC the pending. Progress update: Implementation successful PIS complete Upcoming Communications: CCR (ChMC Deck) – 12/02 Decision in March ChMC: None |  | Implementation date of 6th Dec, the contingency date was 13th Dec. | 
Risks and Issues | N/A |  |  | 
Cost | Forecast to complete delivery against approved MTB funds |  |  | 
Scope | XRN 5576 – Winter Consumption Calculations for Class 4 sites with AMR fitted XRN5794 – Weather API V2 |  |  | 
Complete
On Track
At Risk
Overdue

## Slide 19: 4b. February 2025 Major Release Update

## Slide 20: XRN5818 – February 25 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, BER approved at ChMC on 11/09. Progress Update: Detailed Design Change Pack approved at ChMC – 10/04/24. Build in progress from 16/12/24. Upcoming Communications (Indicative): Implementation Approach/Plan (CHMC Deck) - 12/02 Customer Awareness Session – 04/02 Confirmation of Planned Implementation (Email/Web) – 27/02 Successful/Unsuccessful Implementation (Email/Web) – 28/02 CCR (ChMC Deck) – 30/04 Decision in December ChMC: None |  | ​ Implementation date of 28th February, the contingency date is 07th March. | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5614 -Improving IGT SMP New Connection Process to support accurate and timely Supplier Registrations |  |  | 
Complete
On Track
At Risk
Overdue
Slide updated on 02nd January 2025

## Slide 21: 4c. June 25 Major Release
Scope for Information

## Slide 22
Proposed Scope
Release | June 25 Major Release
Implementation Date & Contingency Date | Implementation Date: 27th June 2025 Contingency Date: 4th July 2025
XRN | Title | Proposer | Benefitting | Funded by | Cost estimate | System components | Solution option approved | Design status | BER approval
5702 | Update to assess the replacement of Facsimile as a form of communication (Modification 0864S) | National Gas Transmission | Shipper, DNO, IGT, NGT | TBC | £150-£250k | UK Link | N/A | In progress Design approval planned Jan ChMC | February ChMC approval
5784 | Modification 0862 Amendments to the current Unidentified Gas Reconciliation Period arrangements | SEFE Energy | Shipper, DNO, NGT | TBC | £85-£115k | UK Link | N/A | Design approved at Dec ChMC | February ChMC approval
Total |  |  |  | Total | £235 - 365k |  |  |  | 
Note: | 
Decision: | Approval of Option 1 or Option 2 as the agreed Major Release scope for June 25.
XRN | Title | Proposer | Benefitting | Funded by | Cost estimate | System components | Solution option approved | Design status | BER approval
5846 | New allowable value (‘M’ - Thermal Mass) for Meter Type Code (H100) | Xoserve | Shipper, DNO, IGT, NGT | TBC | TBC | UK Link | N/A | In progress Design approval expected Mar ChMC | March ChMC approval
5616b | CSEP Annual Quantity Capacity Management | Wales & West Utilities | Shipper, DNO, NGT | TBC | 247k | UK Link | N/A | Design complete, placed On Hold at September ChMC (not approved) | tbc
Total |  |  |  | Total | tbc |  |  |  | 

## Slide 23: June 25 Major Release Scope - Option 1
Deliver XRNs 5702, 5784 and 5846 in June 24 Major Release
Status & Timeline
  Detailed Design for XRN5702 is presented to January ChMC for approval; XRN5784 was approved in December (further investigation pending to understand addition of Supplier ID to associated invoicing per Centrica request).
  BER to be presented to February ChMC meeting for approval of firm delivery costs of both XRNs 5585 and 5720.
  Detailed Design for XRN5846 is underway, costs & delivery timeline are not yet known.
    Design change pack is targeting the March ChMC meeting for approval.
  Updated BER detailing all firm delivery costs will be also provided for March ChMC meeting approval once design on XRN5846 has been completed.
CDSP Recommended Option:
Detailed Design for both XRNs 5702 & 5784 has been published, with both changes having been presented as June 25 Major Release Candidates for some time.
XRN5846 is required in order to align the allowable values in the Metering Related interfaces with the REC data specification.
There are potential synergies between XRNs 5702 & 5846 in terms of UKL documentation updates - combining both XRNs in the same release may mitigate the administrative overhead for customers.

## Slide 24: June 25 Major Release Scope - Option 2
Deliver XRNs 5702, 5784, 5846 and 5616b in June 24 Major Release
Status & Timeline
  Detailed Design for XRN5702 was presented to January ChMC for approval; XRN5784 was approved in December (further investigation pending to understand addition of Supplier ID to associated invoicing per Centrica request), ChMC.
    Detailed Design for XRN5616b has not been approved, placed on hold at September ‘24 ChMC – IGT view is that the change, in it’s current format, is not required to address existing data quality issues.
  Detailed Design for XRN5846 is progressing, the Design change pack is targeting March ChMC meeting approval.
Option Update:
This Option is not recommended on the basis that ChMC has yet to reach consensus on the suitability of XRN5616b; the earliest potential approval for Detailed Design is February ChMC, which creates a delivery risk for a June implementation.

## Slide 25: XRN5702 – Update to assess the replacement of Facsimile as a form of communication (Modification 0864S)
Target Implementation Date / Release DSG Recommendations Requested

## Slide 26
Change Background
Change XRN5702 has been raised to deliver the requirements of Modification 0864. Modification 0864 Update of UNC Code Communication Methods (removal of facsimile/fax) has been raised as it seeks to align obligated Code Communication methods with future communication network changes, attributable to national PSTN decommissioning, and the subsequent retirement of fax devices.
CDSP currently stores FAX as an alternate communication type received as part of registration requests and contact updates from Shippers. Post XRN5702 implementation, FAX will be rejected if provided as a communication type and INT (Email) will be accepted as an alternate communication type, along with mandatory Telephone information.

## Slide 27
Reason for Review
The Detailed Design for change XRN5702 was presented to, and approved by, the Change Management Committee (ChMC) earlier this month.
When discussing the target release date for the change the committee raised challenges on the proposal to include it in the June ‘25 major release. During this discussion it was requested that the implementation date be discussed with DSG to establish if any further clarification is required on the content of the change, the processes impacted and to seek a recommendation on a suitable release date.

## Slide 28
Design Summary
This is a high-level summary of the changes proposed under XRN5702. The full design for the change can be found in the Detailed Design Change Pack (DDCP) here.
Update to allowable values
In files currently containing FAX, this will be removed as an allowable value and INT will be added
Fax number field will be removed from Shared Supply registration files
DN and IGT Portfolio Files
Field currently containing fax number will be increased in size (241) to cater for email address
In fields defining communication type, FAX will be removed, and INT added, as an allowable value
Two new rejection codes will be added
CTT00049 used where FAX is provided as a communication type
CTT00050 where the email address provided does not meet the defined validation criteria
Equivalent changes will also be made to SwitchStream – to remove FAX, add INT and allow “@” to support email data
Reporting changes including updates to existing and new reports to enhance the Emergency Contact Detail process and population have also been identified and included within the approved Detailed Design

## Slide 29
Target Delivery Options and DSG Representatives Views
As per the DDCP, the change was proposed to be included within a major release, however, it could also be delivered via a stand-alone release should stakeholders prefer an implementation date that falls outside of an industry defined release window.
June ’25 Major Release – Option Rejected by ChMC
Originally proposed by Xoserve for the following reasons:
  The related modification has been approved
  This is the next available release
  There is capacity within the release
  Enhanced reporting will be available ahead of the winter period to support improvements in Emergency Contact details
  Allows an extended period for Shippers to ensure emails are populated ahead of the Public Switched Telephone Network (PSTN) being switched off (currently targeted for January 2027)
Points for Discussion at DSG
Do DSG representatives have a view on a preferred delivery date?
Is there a specific lead time that the group feel is required based on the approved Detailed Design?

## Slide 30: 4d. November 2024 Major Release

## Slide 31: XRN5778 – November 24 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, BER approved at ChMC on 12/06. XRN5615, XRN5720 and XRN5585 have all been successfully implemented. Progress Update: Implementation for all XRNs in scope completed – 12/11 Post implementation support for November 24 to be extended to 31/12/2024, to allow for additional monitoring due to the defects identified post implementation Understated CV/WM Capping Enduring Solution Implemented 7/12 MIPI amended 9/12 Drop In Session/SC9 data posted 19/12 Gemini DM Adjustments via EBI 6/1 UIG corrections via Adjustment Invoice 27/1 BCR File Missing Data Interim Solution Implemented 15/12 Enduring Solution Developed/Tested, planned implementation 7/1 on track for all changes in scope Upcoming Communications: CCR (ChMC Deck) – 12/03 Decision in January ChMC: None |  | ​ Implementation date of 08th November for XRN5615 and XRN5720, the contingency date is 15th November Implementation date for XRN5585 - FWACV2 – 12th November, the contingency date is 19th November | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5585 - Flow Weighted Average Calorific Value - Phase 2 Service Improvements (FWACV2) XRN5615 - Establishing/Amending a Gas Vacant Site Process (Modification 0819) XRN5720 - Modification IGT 173 Gateway delivery for RPC backing data |  |  | 
Complete
On Track
At Risk
Overdue
Slide updated on 23rd December 2024

## Slide 32: 4e. DDP Update

## Slide 33: Agenda
Roadmap update
Release Delivery
Latest focus

## Slide 34: 2024-25 DDP Releases
Roadmap | Apr-May 2024 | Jun-Jul | Aug-Sep | Oct-Nov | Dec 24- Jan25 | Feb-Mar
Release 1 2024: Hydrogen Trials | Complete |  |  |  |  | 
Release 2: Hydrogen Trials |  | Complete |  |  |  | 
Release 3: XRN5615 Vacant Sites / AQ at Risk |  |  | Complete |  |  | 
Release 4: XRN5615 Vacant Sites |  |  |  | Complete |  | 
Release 5: Shipper Pack, DN AQ Tracking, IGT Reads |  |  |  |  | In Progress | 
Release 6: Shipper AQ, DN Charging Enhancements, iGT MDD |  |  |  |  |  | Upcoming

## Slide 35: Release 6 Proposed Scope
Goals: | Shippers | DNs | IGTs
Core | AQ Data: AQ Trend Enhancements Portfolio Percentage Breakdown EUC Analysis improvements | DN Charging Improvements: AQ Load band Summary Enhancement Top 15 Invoicing Movements | IGT MDD Mismatch insight
Stretch | Meter Read Rejections Enhancements | Invoicing Data Refinements | 

## Slide 36
Data Discovery Platform | Release 5
Update: Work is underway on delivery of these features, delivery is on track | 
Goals: | Shippers | DNs | IGTs
Core | Shipper pack: Industry read rejections Incorrect read factors | DN Invoice Forecast: December snapshot tracking Commodity forecast Total percentage differences | IGT Reads: Trend analysis on rejection reason codes
Stretch | Shipper Pack: Must read industry performance | DN Invoice Forecast: MPRN level data | IGT Reads: MPRNs not read consistently - reasons

## Slide 37: 5. Change Pipeline

## Slide 38: 2025 Forward View - Change Delivery Plan January 25 – December 2025
Jan-25
June-25
February 25 – Major Release
XRN5614
March-25
Sep-25
Dec-25
June 25 – Major Release
XRN5702, XRN5784, XRN5846 (XRN5616)
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative / Target Implementation Date – Changes are planned for delivery – Funding and/or Implementation Date not yet approved by ChMC
= Implemented Change / Release
Delivery Key
Minor Release 14
(TBC)
Minor Release 15
(TBC)
Slide produced 20th December 2024
November 25 – Major Release
XRN5872 | Mod0884 | Mod0890
February 26 - Major Release
Adhoc Project
XRN5851 – Procurement and Service Activities

## Slide 39: Change Delivery Plan – January 2025 – December 2025
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5614 | Improving IGT SMP New Connection Process to support accurate and timely Supplier Registrations | BUUK | Shipper IGT | Shipper IGT | *£120k revised following design | 28th February 2025 | Major | Firm
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | *£260k revised following design | 27th June 2025 | Major | Indicative
5702 | Mod0864S - Update to assess the replacement of Facsimile as a form of communication | NGT | All DSC Customers | All DSC Customers | £230k *ROM est. | 27th June 2025 | Major | Indicative
5784 | Mod0862 Amendments to the current Unidentified Gas Reconciliation Period arrangements | SEFE | Shipper DN | Shipper | £250k *ROM est. | 27th June 2025 | Major | Indicative
5846 | Update to the Meter product table in UK link to support the Thermal Mass Meter type code | Xoserve | All | TBC | TBC | 27th June 2025 | Major | Indicative
5851 | Mod0868 Change to the current Allocation of Unidentified Gas Statement Frequency and Scope | SEFE | Shipper | Shipper | TBC | June/July 2025 *subject to modification approval | Adhoc | Indicative
5872 | Mod0876S Updates to the Annual Quantity (AQ) amendment process | SEFE | Shipper DN | TBC | £240k *ROM est. | 7th November 2025 *subject to modification approval | Major | Indicative
XXXX | Mod0884 – Extending the PC4 Read Submission Window | OVO | Shipper DN IGT | TBC | £100K *ROM est. | 7th November 2025 *subject to modification approval | Major | Indicative
XXXX | Mod0890 – Update to AQ Correction Processes - Request for Adjustments (RFA) AQ Change | Centrica | Shipper DN | TBC | TBC | 7th November 2025 *subject to modification approval | Major | Indicative

## Slide 40
XRN | Change Title | Proposer | Benefit / Impact | Funding | Status | January ‘25 - ChMC Update
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | Analysis | N/A – performing analysis on data extracts provided by DCC Next steps to be confirmed once analysis is concluded
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Requirements | Use cases, data items and research being undertaken by development team ahead of options being presented to DSC members – target end of 2024 update for DSC customers at DSG on 20th January
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Requirements | Initial analysis shared with Proposer wc 22nd April Requirements baselined and handed over October 2024 Solutions under development – Target February IGT consultation
5806 | CDSP Solution to enable exit of application of User Premises Termination Notice (UPTN) | NGT | All DSC Customers | TBC | Analysis | Change Proposal raised to analyse process and solution impacts that may be necessary to facilitate exit – analysis being planned in with relevant resource
5808 | Providing Notification to DNs and IGTs for Capacity and Nomination Referrals Awaiting Action | Cadent | DN IGT | DN | Requirements | Change Proposal raised by Cadent – engagement with DNs and IGTs held. Requirements baselined October 2024, internal business requirements approved 9th December. Solutions and designs under development – Target February 2025 consultation
5810 | Theft of Gas (ToG) DN Calculation Tool | Cadent | DN | DN | Requirements | Change Proposal raised by Cadent – Solution analysis and ongoing collaboration taking place between CDSP and DN representatives Requirements signed off on 18th December with subject matter experts. Solution and designs under development – target March consultation.
XXXX | Mod0886 - Amend the Code Cut-Off Date to a Rolling Period | SSE | Shipper DN IGT | TBC | Mod Development | Added to change backlog for early visibility as potential that change will require development in 2025/26
XXXX | Mod0896 – Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years | SEFE | Shipper DN IGT | TBC | Mod Development £50K *ROM est. | Following analysis it has been confirmed that the Modification is now targeting a big bang implementation on 1st April 26 *subject to modification approval
Change Backlog Details

## Slide 41: Change Backlog – On Hold Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | January ‘25 ChMC Update
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | *£260k revised following design | Tbc | Agreed following September ChMC that change would be placed on hold whilst data cleansing activities were progressed – change to be revisited in January with DNs / IGTs
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Low Priority – CDSP raised Change Proposal
5701 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert (Modification 0843 / IGT 165) | OVO | Shipper DN IGT | DN IGT | Tbc | Tbc | Continue to support regulatory development and provide update to ChMC once status of Modification changes

## Slide 42: DSC Change Pack Consultation Plan (2 month view)
Jan – 25
Feb - 25
Mar – 25
= Design Change Pack for Consultation
= Solution Option Change Pack for Consultation
= For Information Change Pack
Delivery Key
Slide updated 02nd January 2025
XRN5846 – Update to the Meter product table in UK link to support the Thermal Mass Meter type code
XRN5569 - Contact Data Provision for IGT Customers
XRN 5615 Vacant sites - Service Capacity update

## Slide 43: 6. AOB

## Slide 44: Annex – For Information

## Slide 45: 7. DSC Change Management Committee Update
ChMC 8th January Meeting

## Slide 46: Change Management Committee Update –11.12.24 ChMC Meeting
The Change Management Committee post meeting update can be found here. ​

## Slide 47: 8. REC Change Update

## Slide 48: REC Change
R0120 Search GES API using Meter Serial Number
- CR raised by RECCo, Change will be delivered in February 25. Weekly updates to RTS are now in progress
R0148 Introduction of classification-based access model into the REC in support of Open Data
- Discussions ongoing around solution, and Gas Consolidated Report
R0163 Theft Detection Incentive Scheme (TDIS) Reporting Periods
- Xo responded to consultation
R0229 Supply Point Enquiry API Technical Specification Updates
The following Changes are currently with DCC and the Code Manager:
R0169 Introduction of End of Gate Closure notifications
- Discussions still ongoing w/ DCC around design document. Xo IA to follow.
R0178 Improvements to CSS Business Process Logic
- DCC had questions off the back of their IA. We responded via the Code Manager and are awaiting the output.
November Impact Assessments:
Returned: Consultations for R0163 Theft Detection Incentive Scheme (TDIS) Reporting Periods
Ongoing: RFI for I0200 - Improving address management targets Request for Information & Consultation on I0223 - Reconciliation of Unallocatable Transactions Review
Expected in January:
None confirmed at this stage. Code Manager to review priorities for the New Year and advise expected IAs
Monitoring Until Delivery
R0080 - Improvements to ‘Failed to Deliver’ CSS Messages
R0092a – DCC Service Level Agreements for the Switching Incentive Regime (Alternative)
R0094 - Clarify obligations on gas meter exchanges that occur close to CoS
R0203 - CSS Retry Strategy

## Slide 49
REC Issues List
I0172 - End-to-End New Connections Process Review to Eliminate Issues Related to New Builds and Similar Situations
I0173 - Improvements to the Theft Detection Incentive Scheme (TDIS)
I0174 - Mandating ETTOS follow up
I0175 - Introducing a Reasonable Endeavours Scheme within the REC
I0176 - Creation of an Energy Theft Detection and Resolution Body
I0186 - Non-dual fuel Gas PSR customer
I0196 - Requiring the Supplier/Shipper to validate and enrich the data from the MEM prior to updating this in CDSP (withdrawn)
I0197 - Introducing a process to provide updates during fault resolutions
I0198 - Gas MEMs move towards a single interface for key market messages
I0200 - Improving address management targets
I0218 - Proposal to Enable Broader Use of Retail Energy Location (REL) Data for Non-Switching Applications
I0219 - Stranded RMPs in Defunct Suppliers
I0223 - Reconciliation of Unallocatable Transactions Review
REC Key Terms
GRDA – Gas Retail Data Agent.
IA – Impact Assessment.
DIA – Detailed Impact Assessment.
SPIA – Service Provider Impact Assessment
PIA – Preliminary Impact Assessment
Party IA – Party Impact Assessment
DCC – Data Communications Company
CSS – Central Switching Service
FCR – Final Change Report
ETTOS - Energy Theft Tip Off Service
CM – Code Manager (Includes RPA, RTS & RPS)
TEP – Technical Expert Panel
RPA – REC Performance Assurance (Deloitte)
RTS – REC Technical Services (Capgemini)
RPS – REC Professional Services (Gemserv)
RFI – Request for information
PAB – Performance Assurance Board
CAB – Change Advisory Board

## Slide 50: 9. Portfolio Delivery

## Slide 51: 9. Portfolio Delivery Overview POAP
Please see link to the Change Portfolio POAP here