## Slide 1: XRN5868 – June 25 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | The scope & BER of June 25 Major Release were approved at the ChMC Meetings on 08/01/25 & 12/03/25 respectively. Overall release is tracking to target; Green, Testing has completed, and pre-implementation activities are on track for Go-Live on 27/06. Progress Update: Start-up & Initiation complete -19/05/25 Build complete – 05/05/25 Testing complete – 24/06/25 Implementation on track -27/06/25 PIS on track to commence -27/06/25 Communications Update: GONG Outcome – 26/06/25 Implementation Outcome – 27/06/25 |  | ​ Implementation date of 27th June, the contingency date is 4th July. | 
Risks and Issues | 69676 - June 25 PIS Extension - PIS may be extended because of a request for an additional UIG smear and AMS invoice run |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5846 – New allowable value (M - Thermal Mass) for Meter Type Code (H100) XRN5784 – Modification 0862 Amendments to the current Unidentified Gas Reconciliation Period arrangements |  |  | 
Complete
On Track
At Risk
Overdue
Slide updated on 29th May 2025