## Slide 1: DSC Delivery Sub-Group
Monday 16th December 2024

## Slide 2: 1b. Previous DSG Meeting Minutes and Action Updates
The DSG Actions Log will be published on the DSG pages of Xoserve.com

## Slide 3: 2. Changes in Change Development

## Slide 4: 2a. Change Proposal – For Initial Overview of the Change

## Slide 5: 2a. Change Proposal – For Initial Overview of the Change
2a.i - XRN 5781.1 UNC Modification 0872s Single-sided Nominations for clearing houses of gas exchanges​
2a.ii - XRN 5858 DDP Release 5 2024/2025​

## Slide 6: XRN 5781.1 UNC Modification 0872s Single-sided Nominations for clearing houses of gas exchanges
Customer Parties | Impacted parties
Shipper | Y
Distribution Network Operators (DNOs) | 
National Gas Transmission | Y
IGTs | 
This vote is to approve the change into development | 
Change Description
UNC Modification 0872 creates a change to Gemini that enables eligible Users to elect to submit Single-sided Trade Nominations. This would mean that existing methods of trade clearing which involves nominating both client side and clearing house, logging in using customer (shipper) accounts is superseded. This method is at greater risk of erroneous entries and requires account data to be shared.
DSC Service Area Associated Funding Split | N/A – Gemini Regulatory Investment funded
Proposed Funding split from Proposer | N/A
Change Type | Regulatory
Priority | High
Proposer | National Gas
Change Proposal | Link to CP

## Slide 7: XRN5858 DDP Release 5 2024/2025
Customer Parties | Impacted parties
Shipper | Y
Distribution Network Operators (DNOs) | Y
National Gas Transmission | 
IGTs | Y
This vote is to approve the change into development | 
Change Description
For Release/sprint 5 (December 2024 to January 2025), we intend to continue with the DDP changes to: DN’s – DN Invoice Forecast Shippers – Shipper Pack IGTs – IGT Reads Full summary can be viewed in the Change Proposal
DSC Service Area Associated Funding Split | N/A – General Change Investment funded
Proposed Funding split from Proposer | N/A
Change Type | Non Regulatory
Priority | Medium
Proposer | Xoserve
Change Proposal | Link to CP

## Slide 8: 2b. Change Proposal Initial View Representations

## Slide 9: 2b. Change Proposal Initial View Representations
XRN5846 - New allowable value (M - Thermal Mass) for Meter Type Code (H100)​

## Slide 10
XRN5846 - New allowable value (M - Thermal Mass) for Meter Type Code (H100)
Change proposal XRN5846 has been raised to add ‘M’ as an allowable value in all inbound and outbound files where the field Meter Type Code is utilised
As part of the H100 project thermal mass meters will be used and a new Meter Type Code is required to identify these. The allowable value ‘M’ has been added to the Meter Type Code (A0026) field Market Domain Data (MDD) Meter Product General and now CDSP systems must be updated to reflect this
Customer level requirements have been drafted, provided to the proposer, and submitted for impact assessment

## Slide 11: Next Steps
Any comments are welcomed on the customer requirements presented
The CDSP will continue the initial impact assessments based on them
Lower-level internal CDSP requirements will be developed to meet the customer requirements
Either, High Level Solution Options (HLSO) or a Detailed Design, will be generated and presented back to industry stakeholders

## Slide 12: 2c. Undergoing Solution Options Impact Assessment Review

## Slide 13: 2c. Undergoing Solution Options Impact Assessment Review
None for this meeting.

## Slide 14: 3. Changes in Detailed Design

## Slide 15: 3a. Design Considerations
3a. - XRN 5702 – Update to assess the replacement of Facsimile as a form of communication – Modification 0864S.

## Slide 16: XRN5702 – Update to assess the replacement of Facsimile as a form of communication (Modification 0864S)
Detailed Design

## Slide 17
Background
Change XRN5702 has been raised to deliver the requirements of Modification 0864. Modification 0864 Update of UNC Code Communication Methods (removal of facsimile/fax) has been raised as it seeks to align obligated Code Communication methods with future communication network changes, attributable to national PSTN decommissioning, and the subsequent retirement of fax devices.
CDSP currently stores FAX as an alternate communication type received as part of registration requests and contact updates from Shippers. Post XRN5702 implementation, FAX will be rejected if provided as a communication type and INT (Email) will be accepted as an alternate communication type, along with mandatory Telephone information.

## Slide 18
Detailed Design Summary
The XRN5702 Detailed Design Change Pack contains further details of the change and is summarised here:
File Format Updates
  Registration and Contact Data
  ‘FAX’ is removed, and ‘INT’ (Email) is added, as an allowable value within the S67 record segments (multiple related files)
  File format structure change to remove Field CONTACT_FAX_ NUMBER from the U87 record in the SNO and SNR files
  DN and IGT Portfolio Files
  File format structure changes
    EDL/EQL - ELA_IDENTITY field Length increased to 241 within the B39 record to accommodate Email address
    IDL/IQL - COMMUNICATION_IDENTITY field Length increased to 241 within the B46 record to accommodate Email address
      CONT_ELECTRONIC_COMM_TYPE updated to allow ‘INT’ (Email) as an allowable value with ‘FAX’ removed
    EWS - ELA_IDENTITY field Length increased to 241 within the E24 record to accommodate Email address
      ELA_TYPE updated to allow ‘INT’ (Email) as an allowable value with ‘FAX’ removed
Proposed Email Validations
  Email format validations to be added in processes handling Emergency contacts in the S67 Segment, to ensure any data stored is in a valid email structure i.e. local_part@domain.com
    Please refer to the change pack for full details

## Slide 19
Detailed Design Summary
Proposed New Rejections
  Two new rejections CTT00049 and CTT00050 will be introduced
SwitchStream
  ‘FAX’ will be removed and ‘INT’ for Email will be added as an allowable value in CONT_ELECTRONIC_COMM_TYPE field of the S67 record segment within the below inbound files
    Impacted files defined within the change pack
  Changes to allow ‘@’ as a special character to support submission of an email data in the existing CONTACT_ELECTRONIC_ADDRESS TYPE attribute within S67 record, used in CNF file.
Rejection ID | Rejection Reason Description | Applicable Files
CTT00049 | Invalid communication contact type | Rejection sent in segment S72 in The following response files: CFR, BRR, CRS, OCI, CTR
CTT00050 | Invalid contact email format | 

## Slide 20
Detailed Design Summary
CSS Registrations via API
  Existing APIs for CSS flows will be amended to add ‘INT’ (Email) as an allowable value and remove ‘FAX’ from the validation list. Post this change if any BRN request is received via API and has communication type as ‘FAX’, an error message will be generated from API and the Shipper will be notified with the validation error message ’Request cannot be processed because supplied parameters are invalid’
Report Updates
  Existing contact reports will be amended to remove fax and include email data within the report headings and data
  Proposed new annual report to Shippers and IGTs to provide a view of MPRNs within their respective portfolios that meet the criteria for emergency contact details and if that has been provided
    This is a proposed process enhancement to help customers identify any missing emergency contact information
  Existing weekly contact report to DNs to be updated to include additional data attributes to reflect if mandatory emergency details/email is available for each Supply Meter Points
    This is a proposed process enhancement
  A one-off report is proposed to provide Shipper customers with all active fax entries within the existing UK Link system that will be end dated as part of this change

## Slide 21
Detailed Design Summary
Next Steps:
The Detailed Design Change Pack (DDCP) was issued for consultation on 13th December.
  For reference, the pack is located here
All parties will vote on the outcome of the DDCP consultation at Change Management Committee (ChMC) in January 2025

## Slide 22: 3b. Requirements Clarification
3b.i. – None for this meeting

## Slide 23: 4. Release/Project Updates

## Slide 24: 4. Release/Project Updates
4a. June 25 Major Release proposed scope
4b. XRN5778 November 24 Major Release – Implementation Update
4c. XRN5825 Minor Release drop 13
4d. XRN5818 February 25 Major Release Update
4e. DDP Update

## Slide 25: 4a. June 25 Major Release
Scope for Information

## Slide 26
Proposed Scope
Release | June 25 Major Release
Implementation Date & Contingency Date | Implementation Date: 27th June 2025 Contingency Date: 4th July 2025
XRN | Title | Proposer | Benefitting | Funded by | Cost estimate | System components | Solution option approved | Design status | BER approval
5702 | Update to assess the replacement of Facsimile as a form of communication (Modification 0864S) | National Gas Transmission | Shipper, DNO, IGT, NGT | TBC | £150-£250k | UK Link | N/A | In progress Design approval planned Jan ChMC | February ChMC approval
5784 | Modification 0862 Amendments to the current Unidentified Gas Reconciliation Period arrangements | SEFE Energy | Shipper, DNO, NGT | Shipper | £85-£115k | UK Link | N/A | Design approval planned Dec ChMC | February ChMC approval
Total |  |  |  | Total | £235 - £365k |  |  |  | 
Note: | Scope is for information only – delivery costs for XRN5702 may be subject to update pending completion of Detailed Design process, XRNs 5702 & 5784 are firm contenders, further clarity is required for XRNs 5846 & 5616b - an updated Scope will be submitted to January ChMC for Decision.
Decision: | None.
XRN | Title | Proposer | Benefitting | Funded by | Cost estimate | System components | Solution option approved | Design status | BER approval
5846 | New allowable value (‘M’ - Thermal Mass) for Meter Type Code (H100) | Xoserve | Shipper, DNO, IGT, NGT | TBC | TBC | UK Link | N/A | Proposed to move straight into design | tbc
5616b | CSEP Annual Quantity Capacity Management | Wales & West Utilities | DNO, IGT | DNO, IGT | £319-£385k | UK Link | N/A | DDCP Published 12/08/24 | tbc
Total |  |  |  | Total | tbc |  |  |  | 

## Slide 27: 4b. November 2024 Major Release

## Slide 28: XRN5778 – November 24 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, BER approved at ChMC on 12/06. XRN5615, XRN5720 and XRN5585 have all been successfully implemented. Progress Update: Implementation for all XRNs in scope completed – 12/11 Post implementation support in progress due to complete – 13/12 First usage evidence under review by Business Process consultants Knowledge transfer session in progress, due to complete – 06/12 Implementation prep on track for all changes in scope Upcoming Communications: CCR (ChMC Deck) – 12/03 Decision in December ChMC: None |  | ​ Implementation date of 08th November for XRN5615 and XRN5720, the contingency date is 15th November Implementation date for XRN5585 - FWACV2 – 12th November, the contingency date is 19th November | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5585 - Flow Weighted Average Calorific Value - Phase 2 Service Improvements (FWACV2) XRN5615 - Establishing/Amending a Gas Vacant Site Process (Modification 0819) XRN5720 - Modification IGT 173 Gateway delivery for RPC backing data |  |  | 
Complete
On Track
At Risk
Overdue
Slide updated on 26th November 2024

## Slide 29: 4c. Minor Release 13 Update

## Slide 30: XRN5825 – Minor Release 13 - Status Update
Slide updated on 26th Nov 2024
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking to a Green status. The scope of MiR 13 was presented for information in October ChMC, & there are no external changes associated with this release, therefore, a detailed design change pack will not be issued. The project is currently in its test phase and preparation for implementation – with Implementation on track for 06/12. Progress update: Minor release 13 Performance testing (5576) & Parallel Run (5794) commenced on 18/11. Upcoming Communications: Confirmation of Planned Implementation (Email/Web) – 05/12 Successful/Unsuccessful Implementation (Email/Web) – CCR (ChMC Deck) – 12/02 Decision in December ChMC: None |  | Implementation date of 6th Dec, the contingency date is 13th Dec. | 
Risks and Issues | N/A |  |  | 
Cost | Forecast to complete delivery against approved MTB funds |  |  | 
Scope | XRN 5576 – Winter Consumption Calculations for Class 4 sites with AMR fitted XRN5794 – Weather API V2 |  |  | 
Complete
On Track
At Risk
Overdue

## Slide 31: 4d. February 2025 Major Release Update

## Slide 32: XRN5818 – February 25 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, BER approved at ChMC on 11/09. Progress Update: Detailed Design Change Pack approved at ChMC – 10/04/24. Build to commence – 16/12/24. Upcoming Communications (Indicative): Implementation Approach/Plan (CHMC Deck) - 12/02 Customer Awareness Session (Online Meeting) – tbc Confirmation of Planned Implementation (Email/Web) – 27/02 Successful/Unsuccessful Implementation (Email/Web) – 28/02 CCR (ChMC Deck) – 30/04 Decision in December ChMC: None |  | ​ Implementation date of 28th February, the contingency date is 07th March. | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5614 -Improving IGT SMP New Connection Process to support accurate and timely Supplier Registrations |  |  | 
Complete
On Track
At Risk
Overdue
Slide updated on 28th November 2024

## Slide 33: 4e. DDP Update

## Slide 34: Agenda
Roadmap update
Release Delivery
Latest focus

## Slide 35
Release 2
Jun - Jul
Complete
Release 3 – XRN5615 Vacant Sites / AQ at Risk
Release 4 – XRN5615 Vacant Sites
Release 4 – DN portfolio
Release 5 – XRN 5605 (IGT Mod 159V), XRN 5607 (AQ Corrections)
Release 6 - DN Portfolio History, IGT MDD
Release 1 – Hydrogen Trials
Release 3
Aug - Sep
Release 4
Oct - Nov
Release 5
Dec-Jan
Release 4
Oct - Nov
Release 5
Dec - Jan
Release 6
Feb - Mar
Release 1
Apr – May
Complete
Complete
Complete
Complete
2023
2024
Roadmap
Release 2 – Hydrogen Trials
In Progress
Release 5 - Shipper Pack, DN AQ Tracking, IGT Reads
Complete
Complete

## Slide 36
Data Discovery Platform | Release 4
Goals: Continue work on XRN 5615 Vacant Sites – combination of updates to existing dashboards and new charts and tables continuing from Release 3 Continued data modelling changes and dashboard development to enable vacant sites to update in existing DDP dashboards where relevant | 
Outcome: Continuing the work started in Release 3 to update DDP features for Vacant Sites Changes Relevant dashboards updated to reflect new Vacant Sites processes and new Vacant Sites dashboards to be deployed Delivery on target in November | 

## Slide 37
Data Discovery Platform | Release 5
Update: Work is underway on the detailed design of these features, in conjunction with business SMEs | 
Goals: | Shippers | DNs | IGTs
Core | Shipper pack: Industry read rejections Incorrect read factors | DN Invoice Forecast: December snapshot tracking Commodity forecast Total percentage differences | IGT Reads: Trend analysis on rejection reason codes
Stretch | Shipper Pack: Must read industry performance | DN Invoice Forecast: MPRN level data | IGT Reads: MPRNs not read consistently - reasons

## Slide 38: 5. Change Pipeline

## Slide 39: DSC Change – Review of Key Achievements
Planning and Delivery
3 Major UK Link Releases implemented (1 currently in Post Implementation Support phase)
2 Minor UK Link Releases (1 delivered, 1 on track)
9 Adhoc projects delivered (including UNC Modification process changes)
Total Cost of above projects approx. £1.6m
5 DDP Releases (4 delivered, 1 on track)
3 CMS Releases
Reduced change debt (carried forward change proposals) year on year by 44%
  forecast 14 changes in backlog end of December 2024 compared to 25 changes carried forward from 2023 into 2024
Customer Engagement and Relationship Management
KVI Performance YTD – 95% after 2 quarterly surveys
12 Change Management Committee meetings
12 DSC Delivery Sub-Group meetings
18 DSC Customer Constituency meeting
60 ChMC pre-meets with both Joint Office and all DSC Change Management reps
Delivered 24 pre and post ChMC meeting briefs to customers
Notes: New processes – Addendum process, holding sow process, Finance/FPG process, cancellations/deferrals, sow plan , CI, escalation

## Slide 40: End of Year Recap - Change Delivery Plan January 24 – December 2024
Jan-24
Aug-24
Apr-24
Dec-24
20 DSC Change Proposals and associated projects implemented within Calendar year (2024)
Slide produced 28th November 2024
February 24 – Major Release
XRN5604, XRN5605, XRN5607
June 24 – Major Release
XRN5573b, XRN5675
November 24 – Major Release
XRN5585, XRN5615, XRN5720
Minor Release 12
XRN5727
XRN5665
XRN5690
XRN5695
Minor Release 13
XRN5825
XRN5771
XRN5732
XRN5793
XRN5815
XRN5835
XRN5795

## Slide 41: Delivered Changes - January 2024 – June 2024
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Status
5665 | DN Annual Connection AQ Review Process | SGN | DN Shipper | DN | N/A | January 24 | Adhoc | Delivered
5690 | Billing Calendar CSV file for DSC Customers | E.ON | Shipper DN NGT | Shipper | N/A | January 24 | Adhoc | Delivered
5604 | Shipper Agreed Read (SAR) exceptions process (Modification 0811S) | SEFE | Shipper | Shipper | £150k | February 24 | Major | Delivered
5605 | Amendments to the must read process (IGT159V) | Centrica | Shipper IGT | Shipper IGT | £190k | February 24 | Major | Delivered
5607 | Update to the AQ correction processes (Modification 0816S) | EON Next | Shipper DN IGT | Shipper | £80k | February 24 | Major | Delivered
5727 | Minor Release 12 - XRN5582 Energy Invoice Upload from UK Link to Gemini | Xoserve | CDSP | N/A | N/A | 10th May 24 | Minor | Delivered
5695 | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers (Modification 0854) | NGT | NGT Shipper | NGT | N/A | 22nd May 24 | Adhoc | Delivered
5771 | Amendments to Demand Side Response (DSR) Arrangements – Modification 0866) | NGT | ALL | NGT | N/A | 10th June 24 | Adhoc | Delivered
5732 | Inclusion of IGT MPRNs into specified existing DSC Processes | BUUK | IGT Shipper | TBC | N/A | 1st June 24 | Adhoc | Delivered
5675 | Implementation of 0836S and integration with REC Change R0067 and Modification 0855 - Settlement Adjustments for Supply Meter Points impacted by the Central Switching System P1 Incident (IGT170/171) | SEFE | Shipper | Shipper | £120k (ROM estimate) | 28th June 2024 | Major | Delivered
5573B | Updates to the Priority Consumer process (as designated by the Secretary of State for Business, Energy, and Industrial Strategy - BEIS) | Xoserve | Shipper DN IGT | Shipper DN | £97k | 28th June 2024 | Major | Delivered

## Slide 42: Change Delivery Plan – July 2024 – December 2024
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5815 | New Performance Framework Administrator (PAFA) Service Contract Procurement 2024 | Xoserve | Shipper DN NG IGT | Shipper DN NG IGT | £68k | 5th July 2024 | Adhoc | Firm
5793 | Platform to support Performance Assurance Committee (PAC) | Xoserve | Shipper DN IGT | Shipper DN IGT | £21k | 18th August 2024 (Following BER Approval at ChMC) | Adhoc | Firm
5795 | Business Plan Information Rules Independent Assurance (Mod0841) | Xoserve | Shipper DN NG IGT | Shipper DN NG IGT | £70K | August 2024 | Adhoc | Firm
5835 | Extending the scope of existing ring fenced DSC Change Budget funds to cater for Performance Assurance Committee discretional activities | Xoserve | All | N/A | N/A | Immediately upon approval at ChMC | Adhoc | Firm
5615 | Establishing/Amending a Gas Vacant Site Process (Modification 0819 – IGT168) | Centrica | Shipper DN IGT | Shipper DN | £685k | 8th November 2024 | Major | Firm
5720 | Gateway delivery for RPC backing data (IGT173) | EON | Shipper IGT | Shipper IGT | £50k | 8th November 2024 | Major | Firm
5585 | Flow Weighted Average Calorific Value - Phase 2 Service Improvements | Cadent | DN | DN | £385k | 8th November 2024 | Major | Firm
5825 | Minor Release 13 – delivery of following internal changes; XRN5576 Winter Consumption Calculation for Class 4 with AMR fitted XRN5794 to upgrade Weather API to enable platform update | Xoserve | All | N/A | N/A | 6th December 2024 | Minor | Firm

## Slide 43: 2025 Forward View - Change Delivery Plan January 25 – December 2025
Jan-25
June-25
February 25 – Major Release
XRN5614
March-25
Sep-25
Dec-25
June 25 – Major Release
XRN5616, XRN5702, XRN5784, XRN5846
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative / Target Implementation Date – Changes are planned for delivery – Funding and/or Implementation Date not yet approved by ChMC
= Implemented Change / Release
Delivery Key
Minor Release 14
(TBC)
Minor Release 15
(TBC)
Slide produced 28th November 2024
November 25 – Major Release
Mod0876S | Mod0884 | Mod0890
February 26 - Major Release
Adhoc Project
XRN5851 – Procurement and Service Activities
Adhoc Project
Mod0896

## Slide 44: Change Delivery Plan – January 2025 – December 2025
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5614 | Improving IGT SMP New Connection Process to support accurate and timely Supplier Registrations | BUUK | Shipper IGT | Shipper IGT | *£120k revised following design | 28th February 2025 | Major | Firm
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | *£260k revised following design | 27th June 2025 | Major | Indicative
5702 | Mod0864S - Update to assess the replacement of Facsimile as a form of communication | NGT | All DSC Customers | TBC |  | 27th June 2025 | Major | Indicative
5784 | Mod0862 Amendments to the current Unidentified Gas Reconciliation Period arrangements | SEFE | Shipper DN NGT | TBC | £250k *ROM est. | 27th June 2025 | Major | Indicative
5846 | Update to the Meter product table in UK link to support the Thermal Mass Meter type code | Xoserve | All | TBC | TBC | 27th June 2025 | Major | Indicative
5851 | Mod0868 Change to the current Allocation of Unidentified Gas Statement Frequency and Scope | SEFE | Shipper | Shipper | TBC | June/July 2025 *subject to modification approval | Adhoc | Indicative
XXXX | Mod0876S Updates to the Annual Quantity (AQ) amendment process | SEFE | Shipper DN | TBC | £240k *ROM est. | 7th November 2025 *subject to modification approval | Major | Indicative
XXXX | Mod0884 – Extending the PC4 Read Submission Window | OVO | Shipper DN IGT | TBC | £100K *ROM est. | 7th November 2025 *subject to modification approval | Major | Indicative
XXXX | Mod0890 – Update to AQ Correction Processes - Request for Adjustments (RFA) AQ Change | Centrica | Shipper DN | TBC | TBC | 7th November 2025 *subject to modification approval | Major | Indicative
XXXX | Mod0896 – Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years | SEFE | Shipper DN IGT | TBC | TBC | April 25 ¦ July 25 ¦ April 26 *subject to modification approval | Adhoc | Indicative

## Slide 45
XRN | Change Title | Proposer | Benefit / Impact | Funding | Status | December ‘24 - ChMC Update
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | Analysis | N/A – performing analysis on data extracts provided by DCC Next steps to be confirmed once analysis is concluded
5702 | Update to assess the replacement of Facsimile as a form of communication – Modification 0864S | NGT | All DSC Customers | TBC | Design | Customer requirements and viable solution being progressed into detailed analysis with supplier ahead of Detailed Design being published in December
5784 | Modification 0862 Amendments to the current Unidentified Gas Reconciliation Period arrangements | SEFE | Shipper DN NGT | TBC | Design | Detailed Design issued out for consultation ahead of approval in December ChMC
5846 | Update to the Meter product table in UK link to support the Thermal Mass Meter type code | Xoserve | All | TBC | Analysis | Detailed Analysis being performed ahead of consultation on UK Link Design changes – target January 2025
5851 | Modification 0868 Change to the current Allocation of Unidentified Gas Statement Frequency and Scope | SEFE | Shipper | Shipper | Requirements | Added following Change Proposal being accepted at November ChMC Approach that Change proposal will follow being assessed.
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Requirements | Use cases, data items and research being undertaken by development team ahead of options being presented to DSC members – target end of 2024 update for DSC customers at DSG on 6th December
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Requirements | Initial analysis shared with Proposer wc 22nd April Requirements baselined and handed over October 2024 Solutions under development – Target January 2025 IGT consultation
5806 | CDSP Solution to enable exit of application of User Premises Termination Notice (UPTN) | NGT | All DSC Customers | TBC | Analysis | Change Proposal raised to analyse process and solution impacts that may be necessary to facilitate exit – analysis being planned in with relevant resource
5808 | Providing Notification to DNs and IGTs for Capacity and Nomination Referrals Awaiting Action | Cadent | DN IGT | DN | Requirements | Change Proposal raised by Cadent – engagement with DNs and IGTs held. Requirements baselined October 2024 Solutions and designs under development – Target January 2025 consultation
5810 | Theft of Gas (ToG) DN Calculation Tool | Cadent | DN | DN | Requirements | Change Proposal raised by Cadent – Solution analysis and ongoing collaboration taking place between CDSP and DN representatives
Change Backlog Details

## Slide 46: Change Backlog – On Hold Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | December ‘24 ChMC Update
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | *£260k revised following design | Tbc | Agreed following September ChMC that change would be placed on hold whilst data cleansing activities were progressed – change to be revisited in December
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Low Priority – CDSP raised Change Proposal
5701 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert (Modification 0843 / IGT 165) | OVO | Shipper DN IGT | DN IGT | Tbc | Tbc | Continue to support regulatory development and provide update to ChMC once status of Modification changes

## Slide 47: DSC Change Pack Consultation Plan (2 month view)
Dec – 24
Jan - 25
Feb – 25
= Design Change Pack for Consultation
= Solution Option Change Pack for Consultation
= For Information Change Pack
Delivery Key
Slide produced 28th November 2024
XRN5702 – Update to assess the replacement of Facsimile as a form of communication – Modification 0864S
XRN5846 – Update to the Meter product table in UK link to support the Thermal Mass Meter type code

## Slide 48: 6. AOB

## Slide 49
Supplier Guaranteed Standards of Performance (GSOP) Payment Uplift
Xoserve have noted that Ofgem will increase the compensation payment level of Supplier GSOP payments from 2nd January 2025
  The payment level will increase from £30 to £40
This change has been discussed with Distribution Network (DNs) representatives to establish any potential impacts on them or CDSP processes
It has been ratified that there is no impact to DNs or the CDSP
For reference, the Ofgem announcement can be found here

## Slide 50: Annex – For Information

## Slide 51: 7. DSC Change Management Committee Update
ChMC 11th December Meeting

## Slide 52: Change Management Committee Update –11.12.24 ChMC Meeting
The Change Management Committee post meeting update can be found here. ​

## Slide 53: 8. REC Change Update

## Slide 54: REC Change
R0120 Search GES API using Meter Serial Number
- CR raised by RECCo, Change will be delivered in February 25. Weekly updates to RTS are now in progress
R0148 Introduction of classification-based access model into the REC in support of Open Data
- Discussions ongoing around solution, and Gas Consolidated Report
R0163 Theft Detection Incentive Scheme (TDIS) Reporting Periods
- Xo reviewing ongoing consultation
The following Changes are currently with DCC and the Code Manager:
R0169 Introduction of End of Gate Closure notifications
- Discussions still ongoing w/ DCC around design document. Xo IA to follow.
R0178 Improvements to CSS Business Process Logic
- DCC had questions off the back of their IA. We responded via the Code Manager and are awaiting the output.
November Impact Assessments:
Returned: RFI for I0197 - Introducing a process to provide updates during fault resolutions
Ongoing: N/A
Expected in December:
None confirmed at this stage. There are consultations on the REC Portal which we need to assess and potentially respond to
Monitoring Until Delivery
R0080 - Improvements to ‘Failed to Deliver’ CSS Messages
R0092a – DCC Service Level Agreements for the Switching Incentive Regime (Alternative)
R0094 - Clarify obligations on gas meter exchanges that occur close to CoS
R0203 - CSS Retry Strategy

## Slide 55
REC Issues List
I0172 - End-to-End New Connections Process Review to Eliminate Issues Related to New Builds and Similar Situations
I0173 - Improvements to the Theft Detection Incentive Scheme (TDIS)
I0174 - Mandating ETTOS follow up
I0175 - Introducing a Reasonable Endeavours Scheme within the REC
I0176 - Creation of an Energy Theft Detection and Resolution Body
I0186 - Non-dual fuel Gas PSR customer
I0196 - Requiring the Supplier/Shipper to validate and enrich the data from the MEM prior to updating this in CDSP (withdrawn)
I0197 - Introducing a process to provide updates during fault resolutions
I0198 - Gas MEMs move towards a single interface for key market messages
I0200 - Improving address management targets
I0218 - Proposal to Enable Broader Use of Retail Energy Location (REL) Data for Non-Switching Applications
I0219 - Stranded RMPs in Defunct Suppliers
I0223 - Reconciliation of Unallocatable Transactions Review
REC Key Terms
GRDA – Gas Retail Data Agent.
IA – Impact Assessment.
DIA – Detailed Impact Assessment.
SPIA – Service Provider Impact Assessment
PIA – Preliminary Impact Assessment
Party IA – Party Impact Assessment
DCC – Data Communications Company
CSS – Central Switching Service
FCR – Final Change Report
ETTOS - Energy Theft Tip Off Service
CM – Code Manager (Includes RPA, RTS & RPS)
TEP – Technical Expert Panel
RPA – REC Performance Assurance (Deloitte)
RTS – REC Technical Services (Capgemini)
RPS – REC Professional Services (Gemserv)
RFI – Request for information
PAB – Performance Assurance Board
CAB – Change Advisory Board

## Slide 56: 9. Portfolio Delivery

## Slide 57: 9. Portfolio Delivery Overview POAP
The POAP is available here