## Slide 1: XRN5994 – Emergency Contact Validation Service
Solution Pack

## Slide 2: Change Background
© Xoserve
Change Background
The quality of Emergency Contact data is of the highest priority for all industry parties due to the HSE safety ramifications of inaccurate or incomplete details being provided. In the event of a gas emergency, Distribution Networks (DNs) rely on the accuracy of Shipper-provided Emergency Contact data to ensure DNs (and Shippers) can respond as quickly as possible during a gas supply emergency. Shippers are obliged under the UNC to provide emergency contact details to the DNs for Supply Meter Points (SMPs) that have an AQ > 732,000 kWh.
Problem Statement
The DNs regularly check the validity of the data they receive by calling the held emergency contact numbers that have been provided by Shippers into UK Link systems ahead of the annual Emergency Response exercise each Autumn. During these calls, it has become apparent to the DNs that many of the emergency contact details stored in UK Link systems are either inaccurate or insufficient, leading to issues when the DN attempts to contact the site.
To raise the profile of emergency contact details and highlight the importance of accurate data, the CDSP will conduct a centralised call handling exercise on behalf of the DNs.
Notes: Add bullets

## Slide 3: Change Summary
© Xoserve
Solution Approach
The change requires the CDSP to provide a new Emergency Contacts Validation Service on behalf of the DNs to improve the quality of, and confidence in, the EMR data held on CDSP systems.
As part of this change there are two key objectives to be addressed:
The CDSP to produce a dataset for the ‘Top 200’ SMPs (by AQ) in each LDZ with an AQ above 732,000 kWh. This will be distributed to, and agreed with, the DNs. The CDSP will also produce and distribute two Quarterly reports post the contact validation period.
CDSP will also conduct a centralised call handling exercise on behalf of the DNs over a 4-month period to validate the data held on UK Link systems. The outcome of all the calls will be recorded and reported monthly to the respective DNs and Shippers.
This change is initially scoped as one-off ‘Prove Of Concept’, progressing to an enduring solution will be raised via a separate change request.
Notes: Add bullets

## Slide 4: To-Be Process
© Xoserve
Reuse of current component/function
New component/function
1. Create Dataset of top 200 SMPs from UK Link
CDSP
Initial Dataset
Monthly Report for each month during call handling period
Quarterly Report for the periods following call handling period of top 200 SMPs from UK Link
2. Verify Dataset with the DNs
New Reports
DNs
Shippers
& DNs
4. Generate
Quarterly Reports against original dataset
One-off Solution
Call Handling Period Start
Dataset
1. Call each registered Emergency Contact at SMP site
2. Record call outcomes
3. Generate Monthly Report for call outcomes
Call Handling Period Ends
Shippers & DNs

## Slide 5: Solution Options
© Xoserve
# | Description | Systems and process impacts | Cost Estimate Ranges
1 | Reports run in SAP BO and issued by Customer Ops. Calls made via a non-autonomous solution. | Reporting: Initial ‘Top 200’ report and subsequent 2 ‘Quarterly reports’ to be created and run in SAP BO. Monthly reports templates to be provided to and updated by Call Handlers, then reviewed and issued each month. All reports* to be issued via Customer Ops and to be password protected and distributed via email or huddle to all Shippers and DNs with one or more sites in the ‘Top 200’ portfolio. *For the Initial ‘Top 200 report’ this will only be issued to and reviewed by DNs. Call Handling: All calls to be made between a 4month consecutive period, calls to be manually undertaken and not via any automated call solution. A maximum of 3 call attempts will be made for each contact. | Delivery: £65k - £170k a. Onshore Call Handing. The is reflected by the top end of cost range. b. Offshore Call Handling This would be circa half the onshore cost.
2 | Reports run in SAP BO and issued via IX. Calls made via a non-autonomous solution. (Discounted) | Reporting: Initial ‘Top 200’ report and subsequent 2 ‘Quarterly reports’ to be created and run in SAP BO. Monthly reports templates to be provided to and updated by Call Handlers, then reviewed and issued each month. All reports* to be issued autonomously via IX to all Shippers and DNs with one or more sites in the ‘Top 200’ portfolio. *For the Initial ‘Top 200 report’ this will only be issued to and reviewed by DNs. Call Handling: All calls to be made between a 4month consecutive period, calls to be manually undertaken and not via any automated call solution. A maximum of 3 call attempts will be made for each contact. Discounted: (Updated 08/05/2026) This has been discounted for the ‘Proof Of Concept’ due to increased costs and potential for the reports not to reach the correct internal parties. | Delivery: £100k – £210k (Dependant on location of call handling)

## Slide 6: Assumptions, Dependencies, Risks
© Xoserve
Category | Description
Assumptions | The total number of calls to be made over the 4 months is expected to be up to circa 12,000 based on current assessment of data within UKLink.
 | Average call handling time to be circa 2-3 minutes.
 | The initial dataset may contain IGT sites.
 | The initial dataset will contain the Top 200 SMPs, where the Meter Point Status is not Dead or Extinct.
 | The initial dataset will not contain any NTS sites.
 | The Quarterly reports will not account for AQ movements between the Initial dataset and their delivery. The same SMPs identified as part of the initial dataset will persist across the Quarterly reports.
 | Where there is only one number for an SMP with multiple contacts, a contact can confirm the details for the other emergency contacts rather than needing to speak to each one individually.
 | Independent LDZs will not be considered as part of the dataset.
 | The work to undertake the required call handling service for this change will not commence any earlier than four weeks post award of the contract to the chosen third-party vendor due to required Commercial governance processes.
Dependencies | A reporting template for the Monthly call update reports to be agreed prior to delivery.
 | Call script template to be agreed prior to delivery.

## Slide 7
Appendix

## Slide 8: To Be Process (Written out)
© Xoserve
Creation of the dataset consisting of the ‘Top 200’ SMPs from each LDZ. Dataset will be verified with the DNs and consist of a defined set of data items.
A calling activity will take place, over a 4-month period, to verify each emergency contact associated to each SMP from the dataset.
The results from each call outcome will be captured and provided to the CDSP to form part of the reporting.
To support the calling activity, the CDSP will create a standardised call script to be used for each call to the emergency contacts.
During the call handling period, monthly reporting will be issued to DNs and Shippers. The report will contain the calling activity outcomes for the relevant month.
Following the call handling period, Quarterly reporting will be issued to DNs and Shippers. The report will run against UK Link to capture updates to the initial ‘Top 200’ data set and will be issued for the 2 quarters post the call handling period.
Notes: Add bullets

## Slide 9: Derivation of Call Handling Assumptions
© Xoserve
Maximum calls expected to be circa 12,000 based on an initial data extraction from UK Link we have identified the below emergency contacts associated to the top 200 sites (by AQ) across the 13 LDZs:
Should the 63 sites with 0 emergency contacts be replaced with active SMPs with 3 contacts each, it would result in an additional 189 emergency contacts to be called.
Where these are attempted to be called 3 times then the total additional calls would be 567.
Of the resulting potential 12,273 calls made, should 20% of these be answered on the 1st attempt, it would result in total call volumes of approximately 9,800.
These figures are based on an initial analysis. Detailed dataset extraction will provide more accurate figures which will be produced as part of the dataset creation and subsequent review and finalisation with the DNs.
No. of Emergency Contacts | No. of Related SMPs | Count of Emergency Contacts (to call) | Maximum No. of Calls (3 attempts)
0 | 63 | 0 | 0
1 | 1822 | 1822 | 5466
2 | 155 | 310 | 930
3 | 495 | 1485 | 4455
4 | 40 | 160 | 480
5 | 25 | 125 | 375
Total | 2600 | 3902 | 11706
No. of Emergency Contacts | Where 0 Contacts Replaced With a Site With 3 Contacts | Additional No. of Calls (assuming 3 attempts made)
0 | 189 | 567
1 | 1822 | 5466
2 | 310 | 930
3 | 1485 | 4455
4 | 160 | 480
5 | 125 | 375
Total | 4091 | 12273
Notes: Add bullets

## Slide 10: Derivation of Call Handling Assumptions
© Xoserve
Below is a further breakdown of emergency contacts per LDZ based on the initial data extraction:
Notes: Add bullets

## Slide 11: Discounted Solution Options
© Xoserve
# | Description | Systems and process impacts
3 | Re-use of existing EMR reports and calls made via a non-autonomous solution. (Discounted) | Reporting: Existing reports in UK Link estate to be used instead of Initial ‘Top 200’ report and subsequent 2 ‘Quarterly’ reports. Instead DNs will have to review these reports to create their top 200 list. There is an inflight change to enable Shipper reporting of EMR data so these can be used for shippers. Monthly reports templates to be updated by Call Handlers and reviewed and issued each month. Reports to be issued to issued via Customer Ops/ existing mechanisms to Shippers and DNs with one or more sites in the ‘Top 200’ portfolio. Call Handling: All calls to be made between a period of 4 consecutive months, calls to be manually undertaken and not via any automated call solution. A maximum of 3 call attempts will be made for each site. Discounted: This has been discounted during scoping as they existing infrastructure would not support the required reporting element.