## Slide 1: DSC Delivery Sub-Group
Monday 24th February 2025

## Slide 2: 1b. Previous DSG Meeting Minutes and Action Updates
The DSG Actions Log will be published on the DSG pages of Xoserve.com

## Slide 3: 2. Changes in Change Development

## Slide 4: 2a. Change Proposal – For Initial Overview of the Change

## Slide 5: 2a. Change Proposal – For Initial Overview of the Change
2a.i. XRN 5885 Cease Provision of SC9 Files to Distribution Networks (DNs)
2a.ii. XRN 5888 Minor Release Drop 14 - Parent XRN request
2a.iii. XRN 5887 DDP release 6

## Slide 6: XRN5885 Cease Provision of SC9 Files to Distribution Networks (DNs)
Customer Parties | Impacted parties
Shipper | 
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | 
This vote is to approve the change into development | 
Change Description
The delivery of the FWACV Service (Phase 1) in September 2022 included the provision of daily LDZ Billing CV information (SC9 files) to Shippers, DNs and National Gas. The DNs have concluded that they no longer wish to receive SC9 files from Xoserve. The SC9 information is readily available to DNs from the National Gas data portal (ex MIPI) should it be required.
DSC Service Area Associated Funding Split | Service Area 17: Distribution Network wholly funded activities
Proposed Funding split from Proposer | N/A
Change Type | Non Regulatory
Priority | Low
Proposer | Cadent
Change Proposal | Link to CP

## Slide 7: Proposed scope for information
XRN | Title | Proposer | Benefitting | Funded by
5549 | Automation of the UK Link and Gemini mismatch analysis and correction process | Xoserve | Xoserve | Service & Operate
5769 | Changes required to Broadcast Service (minor changes) | Xoserve | Xoserve | Service & Operate
Release | XRN5888 - Minor Release Drop 14
Implementation date | May 2025 (Indicative Date)
Notes | Change purpose XRN5549 removal of potential need for out of hours working arrangements to process some of the timebound fixes​ alongside helping to ensure correct transport billing and supply point register entries. XRN5769 to how view Extract Request search results are displayed, meaning a reduction in manual effort. Monthly status updates will be provided to ChMC throughout the delivery. As the release will be funded from the service & operate budget there will be no requirement for a BER to approve draw down of General Change investment budget. A closedown report will be presented to ChMC upon completion of this release.
Decision | None required; update for information only

## Slide 8: XRN5887 DDP Release 6 2024/2025
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | X
This vote is to approve the change into development | 
Change Description
Following prioritisation discussions at ChMC, in release/sprint 6 (February - March 2025), we intend to continue with the DDP changes to: DN’s – DN Charging Improvements Shippers – AQ Data/Meter Read Rejections IGTs – MDD Mismatch
DSC Service Area Associated Funding Split | As agreed within the Business Plan
Proposed Funding split from Proposer | N/A
Change Type | Release
Priority | N/A
Proposer | Xoserve
Change Proposal | Link to CP

## Slide 9: 2b. Change Proposal Initial View Representations

## Slide 10: 2b. Change Proposal Initial View Representations
None for this meeting.

## Slide 11: 2c. Undergoing Solution Options Impact Assessment Review

## Slide 12: 2c. Undergoing Solution Options Impact Assessment Review
None for this meeting.

## Slide 13: 3. Changes in Detailed Design

## Slide 14: 3a. Design Considerations
3a.i. XRN 5846 – Update to the Meter product table in UK link to support the Thermal Mass Meter type code

## Slide 15: XRN 5846 - New allowable value (M - Thermal Mass) for Meter Type Code (H100)
Detailed Design

## Slide 16
Background
The allowable values utilised within the Review of Gas Metering Arrangement (RGMA) files are owned and maintained under the Retail Energy Code (REC). This data is provided to the Central Data Service Provider (CDSP) by Shipper Users and Meter Asset Managers (MAMs) as part of the RGMA process. The data is issued out by the CDSP as part of other downstream processes such as Shipper Transfers.
As part of the H100 project, thermal mass meters will be used and a new Meter Type Code was created to identify these. The allowable value ‘M’ has been added to the Meter Type Code (A0025) field as part of the Market Domain Data (MDD) and now CDSP systems must be updated to reflect this.
The change would the allowable values in all connected parties’ systems to be aligned to ensure the flow of meter information and accurate maintenance of the Supply Point Register.

## Slide 17
Detailed Design Summary
The XRN5846 Detailed Design Change Pack contains further details of the change and is summarised here.
Solution:
With the introduction of thermal mass meters as part of the H100 project, we must ensure that meter asset data can be shared and stored accurately for all meter types across the gas industry and stakeholder systems. Change proposal XRN5846 has been raised to add ‘M’ (Thermal Mass) as an allowable value in all inbound and outbound interfaces where the field Meter Type/Meter Type Code is utilised in order to ensure no failures occur.
This change will introduce the following:
All the interfaces (Files/APIs) which have Meter Type/Meter Type Code field will be updated to include the values provided within the REC Meter Product General (MPG) data for Meter Type Code.
These interfaces will be tested to prove the message communication happens correctly with the Meter Type/Meter Type Code value M. This includes ensuring data flows into GES.
Changes will be made to the RGMA validation check framework program to include value M as provided within the REC MPG data records for Meter Type Code.
The Meter Type/Meter Type Code value will flow to reporting systems using the existing route and it will appear in the reports.
All impacted UK Link Interface Documents to be updated.

## Slide 18: Next Steps
The Detailed Design Change Pack (DDCP) was issued for consultation on 17th February’25.
  Located here https://www.xoserve.com/change/change-packs/?search=
Shippers, DNs and IGTs will vote on the outcome of the DDCP consultation at ChMC in March’25.

## Slide 19: 3b. Requirements Clarification
None for this meeting.

## Slide 20: 4. Release/Project Updates

## Slide 21: 4. Release/Project Updates
4a. XRN5825 Minor Release drop 13
4b. XRN5818 February 25 Major Release Update
4c. XRN5778 November 24 Major Release
4d. DDP Update

## Slide 22: XRN 5825 Minor Release 13 Update

## Slide 23: XRN5825 – Minor Release 13 - Status Update
Slide updated on 28th Jan 2025
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking to a Green status. Minor Release 13 was successfully implemented on 6th Dec. First usage activities are complete, and we exited the post-implementation support phase with no issues raised. Closedown activities almost complete with the h approval of the CCR in February ChMC the only pending activity. Progress update: Implementation successful PIS complete Decision in February ChMC: Approval of the CCR |  | Implementation date of 6th Dec, the contingency date was 13th Dec. | 
Risks and Issues | N/A |  |  | 
Cost | Forecast to complete delivery against approved MTB funds |  |  | 
Scope | XRN 5576 – Winter Consumption Calculations for Class 4 sites with AMR fitted XRN5794 – Weather API V2 |  |  | 
Complete
On Track
At Risk
Overdue

## Slide 24: XRN 5818 February 2025 Major Release Update

## Slide 25: XRN5818 – February 25 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, BER approved at ChMC on 11/09. Progress Update: Detailed Design Change Pack approved at ChMC – 10/04/24. Build Completed – 17/01/25 ST Testing in progress from 13/01/25; complete by 31/01 UAT to commence from 03/02/25 Upcoming Communications (Indicative): Implementation Approach/Plan (CHMC Deck) – 30/01 Training Sessions (Online) – 04/02 (tbc) Confirmation of Planned Implementation (Email/Web) – 27/02 Successful/Unsuccessful Implementation (Email/Web) – 28/02 CCR (ChMC Deck) – 30/04 Decision in December ChMC: None |  | ​ Implementation date of 28th February, the contingency date is 07th March. | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5614 -Improving IGT SMP New Connection Process to support accurate and timely Supplier Registrations |  |  | 
Complete
On Track
At Risk
Overdue
Slide updated on 30th January 2025

## Slide 26: XRN5778 November 24 Major Release

## Slide 27: XRN5778 – November 24 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, BER approved at ChMC on 12/06. XRN5615, XRN5720 and XRN5585 have all been successfully implemented and PIS completed. Progress Update: Implementation for all XRNs in scope completed – 12/11 CCR update/review in progress to be completed – 21/02 Understated CV/WM Capping The below activities have now been completed. Enduring Solution Implemented 7/12 MIPI amended 9/12 Drop In Session/SC9 data posted 19/12 Gemini DM Adjustments via EBI 6/1 UIG corrections via Adjustment Invoice 27/1 BCR File Missing Data Interim Solution Implemented 15/12 Enduring Solution Developed/Tested, planned implementation 7/1 on track for all changes in scope Upcoming Communications: CCR (ChMC Deck) – 12/03 Decision in February ChMC: None |  | ​ Implementation date of 08th November for XRN5615 and XRN5720, the contingency date is 15th November Implementation date for XRN5585 - FWACV2 – 12th November, the contingency date is 19th November | 
Risks and Issues | None |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5585 - Flow Weighted Average Calorific Value - Phase 2 Service Improvements (FWACV2) XRN5615 - Establishing/Amending a Gas Vacant Site Process (Modification 0819) XRN5720 - Modification IGT 173 Gateway delivery for RPC backing data |  |  | 
Complete
On Track
At Risk
Overdue
Slide updated on 30th January 2025

## Slide 28: DDP Update

## Slide 29: Agenda
Release Delivery
Latest focus
DDP Workgroup & Contact information

## Slide 30
Data Discovery Platform | Release 6
Update: Release delivery is underway following ChMC prioritization agreement last month. | 
Goals: | Shippers | DNs | IGTs
Core | AQ Data: AQ Trend Enhancements Portfolio Percentage Breakdown EUC Analysis improvements | DN Charging Improvements: AQ Load band Summary Enhancement Top 15 Invoicing Movements | IGT MDD Mismatch insight
Stretch | (R5) Shipper Pack: Must read industry performance Meter Read Rejections Enhancements | Invoicing Data Refinements | 

## Slide 31
Data Discovery Platform | Release 5
Update: Release 5 deployment during DDP Maintenance hours on 31st Jan 2025. As this is a Friday, features will be available, and first use assurance will begin on Monday 3rd February As indicated at the January ChMC, the stretch feature “Must read industry performance” will move to into the release 6 delivery window. This is in addition to the agreed scope of Release 6. | 
Goals: | Shippers | DNs | IGTs
Core | Shipper pack: Industry read rejections Incorrect read factors | DN Invoice Forecast: December snapshot tracking Commodity forecast Total percentage differences | IGT Reads: Trend analysis on rejection reason codes
Stretch | Shipper Pack: Must read industry performance (Delivery in R6 Window) | DN Invoice Forecast: MPRN level data | IGT Reads: MPRNs not read consistently - reasons

## Slide 32: DDP Assurance Workgroup
For all DDP Releases we would like to request volunteers from the DDP User community to sponsor planned features.
The objective is to increase engagement in new Release features and help ensure we deliver features that meet the needs of our users.
This would involve:
  Contributing and supporting the relevant User Stories that sit behind proposed features, to promote benefits to wider industry
  Testing and First Usage assurance of new/updated dashboard features, to confirm satisfaction with the delivered content
For Release 5 we welcome all users to support first usage by assuring the new delivered features
For Release 6 onwards we will seek sponsors at the beginning of the process
Should you be able to support on Release 5 or 6 please contact the team via our operational email box account (ddp@xoserve.co.uk)

## Slide 33: DDP Team Contact Details
DDP Issues:
If you have an issue relating to DDP which you require support with, please raise a ticket via ‘help and support’ on xoserve.com here. This will ensure the issue is dealt with promptly and provides an audit trail
DDP Queries / Development / Shipper Forum:
If you have any queries, ideas or suggestions for future DDP features or questions relating to the DDP Shipper Forum please drop an email to the DDP Operational team via our box account: ddp@xoserve.co.uk
For avoidance of doubt, if you have an issue with DDP, the quickest way for a resolution is to raise a ticket

## Slide 34: 5. Change Pipeline

## Slide 35: 2025 Forward View - Change Delivery Plan January 25 – December 2025
Jan-25
June-25
February 25 – Major Release
XRN5614
March-25
Sep-25
Dec-25
June 25 – Major Release
XRN5784, XRN5846
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative / Target Implementation Date – Changes are planned for delivery – Funding and/or Implementation Date not yet approved by ChMC
= Implemented Change / Release
Delivery Key
Minor Release 14
(TBC)
Minor Release 15
(TBC)
Slide produced 29th January 2025
November 25 – Major Release
XRN5702 | XRN5872 | Mod0890 | XRN5616b
February 26 - Major Release
Mod0890
Adhoc Project
XRN5851 – Procurement and Service Activities
Minor Release 16
(TBC)

## Slide 36: Change Delivery Plan – January 2025 – December 2025
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5614 | Improving IGT SMP New Connection Process to support accurate and timely Supplier Registrations | BUUK | Shipper IGT | Shipper IGT | *£120k revised following design | 28th February 2025 | Major | Firm
5784 | Mod0862 Amendments to the current Unidentified Gas Reconciliation Period arrangements | SEFE | Shipper DN | Shipper | £115k | 27th June 2025 | Major | Firm
5846 | Update to the Meter product table in UK link to support the Thermal Mass Meter type code | Xoserve | All | TBC | £100k | 27th June 2025 | Major | Firm
5851 | Mod0868 Change to the current Allocation of Unidentified Gas Statement Frequency and Scope | SEFE | Shipper | Shipper | TBC | June/July 2025 *subject to modification approval | Adhoc | Firm
5702 | Mod0864S - Update to assess the replacement of Facsimile as a form of communication | NGT | All DSC Customers | Shipper DN | £230k *ROM est. | 7th November 2025 *options being presented @ Feb ChMC | Major | Indicative
5872 | Mod0876S Updates to the Annual Quantity (AQ) amendment process | SEFE | Shipper DN | TBC | £240k *ROM est. | 7th November 2025 *subject to modification approval | Major | Indicative
XXXX | Mod0890 – Update to AQ Correction Processes - Request for Adjustments (RFA) AQ Change | Centrica | Shipper DN | TBC | TBC | 7th November 2025 *subject to modification approval | Major | Indicative
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | *£260k revised following design | 7th November 2025 *subject to definitive decision between IGTs and DNs | Major | Indicative
XXXX | Mod0884 – Extending the PC4 Read Submission Window | OVO | Shipper DN IGT | TBC | £100K *ROM est. | February 2026 *subject to modification approval | Major | Indicative

## Slide 37
XRN | Change Title | Proposer | Benefit / Impact | Funding | Status | February ‘25 - ChMC Update
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | Analysis | N/A – performing analysis on data extracts provided by DCC Next steps to be confirmed once analysis is concluded
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Requirements | Use cases, data items and research being undertaken by development team ahead of options being presented to DSC members – target Q1 2025 update for DSC customers at DSG
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Requirements | Solution Options under development – Target February IGT consultation ahead of March ‘25 Change Pack
5806 | CDSP Solution to enable exit of application of User Premises Termination Notice (UPTN) | NGT | All DSC Customers | TBC | Analysis | Change Proposal raised to analyse process and solution impacts that may be necessary to facilitate exit – analysis being planned in with relevant resource
5808 | Providing Notification to DNs and IGTs for Capacity and Nomination Referrals Awaiting Action | Cadent | DN IGT | DN | Requirements | Engagement with DNs and IGTs held. Requirements baselined October 2024, internal business requirements approved 9th December. Solutions and designs under development – Target February 2025 consultation
5810 | Theft of Gas (ToG) DN Calculation Tool | Cadent | DN | DN | Requirements | Change Proposal raised by Cadent – Solution analysis and ongoing collaboration taking place between CDSP and DN representatives Requirements signed off on 18th December with subject matter experts. Solution and designs under development – target March consultation.
5885 | Cease Provision of SC9 Files to Distribution Networks (DNs) | Cadent | DN | DN | Impact Assessment | Change Proposal raised by Cadent on behalf of DNs – seeking to prevent SC9 files being delivered to DNs as these are no longer required. Changes being impact assessed ahead of confirmation on next steps
XXXX | Mod0886 - Amend the Code Cut-Off Date to a Rolling Period | SSE | Shipper DN IGT | TBC | Mod Development | Added to change backlog for early visibility as potential that change will require development in 2025/26 Anticipated Minor / Adhoc UK Link Delivery
XXXX | Mod0896 – Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years | SEFE | Shipper DN IGT | TBC | Mod Development £50K *ROM est. | Following analysis it has been confirmed that the Modification is now targeting a big bang implementation on 1st April 26 Anticipated Minor / Adhoc UK Link Delivery
Change Backlog – ‘In Progress’ Details

## Slide 38: Change Backlog – On Hold Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | February ‘25 ChMC Update
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | *£260k revised following design | Tbc | Agreed following September ChMC that change would be placed on hold whilst data cleansing activities were progressed – change to be revisited in January with DNs / IGTs
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Low Priority – CDSP raised Change Proposal
5701 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert (Modification 0843 / IGT 165) | OVO | Shipper DN IGT | DN IGT | Tbc | Tbc | Continue to support regulatory development and provide update to ChMC once status of Modification changes

## Slide 39: DSC Change Pack Consultation Plan (2 month view)
Feb – 25
Mar - 25
Apr – 25
= Design Change Pack for Consultation
= Solution Option Change Pack for Consultation
= For Information Change Pack
Delivery Key
Slide produced 29th January 2025
XRN5846 – Update to the Meter product table in UK link to support the Thermal Mass Meter type code
XRN5569 - Contact Data Provision for IGT Customers
XRN5808 - Providing Notification to DNs and IGTs for Capacity and Nomination Referrals Awaiting Action
XRN5781.2 – Change to EIC Code(s) within Gemini

## Slide 40: 6. AOB

## Slide 41: Annex – For Information

## Slide 42: 7. DSC Change Management Committee Update
Wednesday 12th February 2025

## Slide 43: Change Management Committee Update – 12/02/2025 ChMC Meeting
The Change Management Committee post meeting update can be found here. ​

## Slide 44: 8. REC Change Update

## Slide 45: REC Change Overview
On the next few pages are the usual slides on the ongoing Changes/Issues and updates. We would like to draw you attention to the following updates which we will discuss at the meeting.
R0148 - Introduction of classification-based access model into the REC in support of Open Data
- Discussions ongoing around solution with RTS, RECCo and Xo.
I0219 - Stranded RMPs in Defunct Suppliers
- To allow sites that are at terminated status to move to another Shipper/Supplier in a market exit instance. Will replace Derogation 15 (which has been extended to April 2025). Change is going to be included in the scope for R0178.
R0178 - Improvements to CSS Business Process Logic
- RTS are currently developing the solution (now inc. I0219) and intend on bringing the proposed solution back to Technical Change Workshop (TCW) in Feb 25, following that a DIA will be completed with CSS
I0200 - Improving address management targets
- Xo responded to RFI on 10/01. DNO targeted IA ongoing for Solution Analysis Submissions. Response due 28/02.
The following issues are due to be raised the upcoming Change Issues Group, and we will be available to support the Code Manager in providing understanding of any existing gas processes, support their assessment of the issue. They are currently in the very early assessment stages.
I0196 - Requiring the Supplier/Shipper to validate and enrich the data from the MEM prior to updating this in CDSP
I0198 - Metering Asset Manager (MAM) Communication Method Register (previously, Gas MEMs move towards a single interface for key market messages)

## Slide 46: 9. Portfolio Delivery

## Slide 47: 9. Portfolio Delivery Overview POAP
The POAP is available here.